## Slide 1
Oracle Application Testing Suit Project
Kick-Off
July 29th 2019

## Slide 2: Agenda
Introduction
Project Scope
Execution Approach
High Level Plan & Current Status
Next Action & Support Required
Q&A

## Slide 3: Introduction:
Subhasis Jana - Project Manager
Sujit Swain– Oracle application testing suite consultant
Functional Leads (IBM)
Business Process Owners (Ma’aden)

## Slide 4: Project Scope:
At present no tools available in the project to automate testing of functional/technical changes for Oracle EBS.
Implementation Scope:
Setup Oracle application testing suite to fulfil the test requirements of Oracle EBS through Oracle Test Manager functionality.
Target to automate 20 Test Cases for this project.
Perform test automation by automating repeatable, reusable tests cases using tools and enabling execution.
Benefit:
OATS will help to reduce testing time and efforts and increase efficiency and productivity in testing cycle.
OATS will help to plan, organize, document, and manage the entire application testing process
Track defects and manage test requirements
Web-based test management solution

## Slide 5: Oracle Test Manager Flow:
Integrated test modules provide complete test process management.
Test Requirements, Test Plan, Test Cases, Test Execution and Issues (Defects), Dashboard.
Document Test Requirement
Test Plan
Write Test Cases (Scripts)
Execute Test Cases
File Defects Found By Test execution
View Reports & Dashboard

## Slide 6
  Inception (Planning):
    Kick-Off
    On-board Project team
    Finalize pre-requisite infrastructure for OATS, EBS application and Licenses
    Project Plan & Tracker
  Elaboration & Construction (Design & Build):
    Installation and configuration of OATS
    Develop functional, system test plans and schedules
    Setup Oracle Applications Test Manager for Test Case Management
    Develop Automated Test script as part of the Testing using OATS Tool. (upto 20 test cases per month)
  Transition (Testing):
    System testing
    Record and report test results to Ma'aden & Complete test documentation
    Conduct UAT and Sign-Off
  Sign Off Criteria:
    IBM to submit Implementation Completion report to Ma'aden. OATS Implementation Completion report deliverable consists of:
      Test Automation Process
      Test Automation Framework
Execution Approach:

## Slide 7
High Level Project Plan:
  Overall Project Plan is for 6 weeks out of which 1 week for Planning, 4 weeks for Design & Build and 4 weeks for Testing. Project completion date is 9th Sep-2019
Deliverables:
Weekly updates to be published in weekly review meeting
Test plan and schedule
Implementation Completion Report to be submitted

## Slide 8
Progress so far:
Support Required:
    Identify Business Process Owners
    Validate test scenarios
Kick Off – Planned on 29th Jul-2019
Obtain Server & OATS license – Window server will be ready in next couple of days; OATS license is available
Onboard IBM Project team to proceed with Inception phase – OATS consultant is already onboarded
Infrastructures readiness for OATS system Installation – IBM DBAs will install/configure OATS when the above windows server is ready
Identify Business Process Owners – Open item
Assumptions:
    Windows server will be commissioned by 29th Jul-2019

## Slide 9: Test Scenarios (20)

## Slide 10
Backup slides