## Sheet1
Sl. No. | Module | Scenarios | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Manual Effort | Automation Effort | Effort Save | Updates/Comments
1 | Purchasing | Purchase Requisition Creation under Purchasing Preparer Organization Unit as (MWSPC_PURCHASING_PREPARER) for single user(e:g - BRAHMEG) | PR_RequisitionCreation_ORG_Unit_MWSPC_001 | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-10-01 | Pass
2 | Purchasing | Purchase Requisition Creation without entering Charge Account details | PR_RequisitionCreation_WO_ChargeAccount_N_002 | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-03 | Pass
3 | Purchasing | Purchase Requisition Creation with Need-By-Date as past date | PR_RequisitionCreation_NeedByDateAsPast_N_003 | 2019-10-06 | 2019-10-06 | 2019-10-06 | 2019-10-06 | Pass
4 | Purchasing | Validate the status details of created Reqution | PR_RequisitionStatusValidation_004 | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2019-10-09 | Pass
5 | Purchasing | Validate the hirchecy level details of a approved requestion | PR_ApprovedRequisitionHierarchy_005 | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2019-10-10 | Pass
6 | Purchasing | Create the Purchase Requisition with type as Service using search option | PR_RequisitionCreation_TypeAsServiceUsingSearchOption_006 | 2019-10-13 | 2019-10-13 | 2019-10-13 | 2019-10-13 | Pass
7 | Purchasing | Purchase Requisition Creation with mandatory field only | PR_RequisitionCreationMandatoryFieldOnly_007 | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-10-14 | Pass
8 | Purchasing | Search the requsition status in different Organization Unit (MPC PURCHASING BUYER) Requisition created on MWSPC_PURCHASING_PREPARER Try to find out in MPC PURCHASING BUYER | PR_RequisitionSearchInOther_ORG_Unit_008 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | Pass
9 | Purchasing | Return list of requisition number on Blank Search | PR_RequisitionBlankSearch_009 | 2019-10-16 | 2019-10-16 | 2019-10-16 | 2019-10-16 | Pass
10 | Purchasing | Return list of approved requisition number | PR_RequisitionApprovedSearch_010 | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2019-10-17 | Pass
11 | Purchasing | Create and approve the requisition(Whole process) | PO_CreateRequisitionAndApproval_011 | 2019-09-17 | 2019-09-30 | 2019-09-30 | 2019-09-30 | Pass
12 | Purchasing | Return list of InProcess requisition details | PR_RequisitionInProcessSearch_001 | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2019-09-18 | Pass
13 | Purchasing | Return list requisition details for Specific Date Range | PR_SpecificDateRangePeriod_RequisitionSearch_002 | 2019-09-19 | 2019-09-19 | 2019-09-19 | 2019-09-19 | Pass
14 | Purchasing | Validate the Buyer from the purchase requisition | PR_BuyerVerificationOnRequisition_003 | 2019-09-22 | 2019-09-22 | 2019-09-22 | 2019-09-22 | Pass
15 | Purchasing | Assign buyer on In Process requisition | PR_AssignBuyerOnInProcessRequisition_004 | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-09-23 | Pass
16 | Purchasing | Assign buyer on Approved requisition | PR_AssignBuyerOnApprovedRequisition_005 | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2019-09-24 | Pass
17 | Purchasing | Change the Buyer in a Requisition when its Approved status | PO_ChangeBuyerInRequisition_002 | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-09-25 | Pass