## Sheet1
Sl. No. | Module | Scenarios | Test Cases Steps | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | HCM | Absence Reason view | 1)LogIn the application 2)Handle Welcome Screen 3)Click on My_Client_Groups 4)Click on Absence Reason 5)Provide the Name and click on search 6)Fetch the results detail like name, satus and location 7)Validate the output with input 8)LogOut and close the application | HCM_AbsenceReason_0022 | 2020-06-18 | 2020-06-18 | 2020-06-18 | 2020-06-18 | Pass | HCM Cloud
2 | HCM | Absence Reason on invalid inputs(negative scenario) | 1)LogIn the application 2)Handle Welcome Screen 3)Click on My_Client_Groups 4)Click on Absence Reason 5)Provide the invalid Name and click on search 6)Check the test results details (No results found should return) 7)Validate the output with input 8)Close the application | HCM_Invalid_AbsenceReason_0023 | 2020-06-21 | 2020-06-21 | 2020-06-21 | 2020-06-21 | Pass | HCM Cloud
3 | HCM | Absence Certification | 1)LogIn the application 2)Handle Welcome Screen 3)Click on My_Client_Groups 4)Click on Absence Reason 5)Provide the Name and click on search 6)Fetch the results detail like name, satus and location 7)Validate the output with input 8)LogOut and close the application | HCM_AbsenceCertificate_0024 | 2020-06-22 | 2020-06-22 | 2020-06-22 | 2020-06-22 | Pass | HCM Cloud
4 | HCM | Absence Certification on invalid inputs(negative scenario) | 1)LogIn the application 2)Handle Welcome Screen 3)Click on My_Client_Groups 4)Click on Absence Reason 5)Provide the invalid Name and click on search 6)Fetch the error results and and validate 7)LogOut and close the application | HCM_Invalid_AbsenceCertification_0025 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 2020-06-23 | Pass | HCM Cloud
5 | HCM | Absence Plan | 1)LogIn the application 2)Handle Welcome Screen 3)Click on My_Client_Groups 4)Click on Absence Plan 5)Provide thePlan Name and click on search 6)Fetch the results detail like plan name, plan type. managment etc 7)Validate the output with input 8)LogOut and close the application | HCM_AbsencePlan_0026 | 2020-06-24 | 2020-06-24 | 2020-06-24 | 2020-06-24 | Pass | HCM Cloud
6 | HCM | Absence Plan on invalid inputs(negative scenario) | 1)LogIn the application 2)Handle Welcome Screen 3)Click on My_Client_Groups 4)Click on Absence Plan 5)Provide the invalid Plan Name and click on search 6)Fetch the error message and validate 7)LogOut and close the application | HCM_Invalid_AbsencePlan_0027 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-06-25 | Pass | HCM Cloud
7 | HCM | AbsenceType(Search) | 1)LogIn the application 2)Handle Welcome Screen 3)Click on My_Client_Groups 4)Click on Absence Type 5)Provide theType Name and click on search 6)Fetch the results detail like Type name etc 7)Validate the output with input 8)LogOut and close the application | HCM_AbsenceType_0028 | 2020-06-28 | 2020-06-28 | 2020-06-28 | 2020-06-28 | Pass | HCM Cloud
8 | HCM | AbsenceType on invalid inputs(negative scenario) | 1)LogIn the application 2)Handle Welcome Screen 3)Click on My_Client_Groups 4)Click on Absence Type 5)Provide the invalid Type Name and click on search 6)Fetch the error results detail and validate 9)LogOut and close the application | HCM_Invalid_AbsenceType_0029 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | Pass | HCM Cloud
9 | HCM | Manage Locations(Edit Location) | 1)Log into Oracle 2)Search Location 3)To update the location, click Edit Icon 4)Select Effective Start Date, Click OK 5)Edit desired location information by selecting Edit 6)Click Submit 7)Click Yes 8)Click OK 9)Click Done to return to overview page | HCM_ManageLocations_EditLocation_0030 | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-06-30 | Pass | HCM Cloud
10 | HCM | Manage Locations(Correction Location) | 1)Log into Oracle 2)Search Location 3)To correct the location, click Edit Icon 4)Select Effective Start Date, Click OK 5)Edit desired location information by selecting Edit 6)Click Submit 7)Click Yes 8)Click OK 9)Click Done to return to overview page | HCM_ManageLocations_CorrectionLocation_0031 | 2020-07-01 | 2020-07-01 | 2020-07-01 | 2020-07-01 | Pass | HCM Cloud
11 | HCM | Manage Locations(Create new Location) | 1) Log into Oracle 2) Click Create 3) Enter the effective start date into the field 4) Select Location Set 5) Enter Location Name, Code and Description into fields 6) Select a status 7) To select a country, select desired country from drop down menu 8) Enter Address Information 9) Enter additional Information 10) Click Submit 11) Click Yes 12) Click OK 13) Click Done to return to overview page | HCM_ManageLocations_CreateLocation_0032 | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-07-02 | Pass | HCM Cloud
12 | HCM | Manage Job Families(Create New) | 1. Login to Oracle Cloud HCM Applications Homepage 2. Click Login 3. Click the Navigator Icon, My Client Groups, Workforce Structures" 4. Click on tasklist icon present on the right side of the application window. 5. Click on task name - 'Manage Job Families' to navigate to task 6. To create a job family, click Create 7. Enter the Effective Start Date, Name, Context Value, Attachment, Action Reason and Status 8. To submit the new job family, click Submit 9. Click Yes 10. Click OK | HCM_ManageJobFamilies_Create_JobFamilies_0033 | 2020-07-05 | 2020-07-05 | 2020-07-05 | 2020-07-05 | Pass | HCM Cloud
13 | HCM | Manage Job Families(Update) | 1. Login to Oracle Cloud HCM Applications Homepage 2. Click Login 3. Click the Navigator Icon, My Client Groups, Workforce Structures" 4. Click on tasklist icon present on the right side of the application window. 5. Click on task name - 'Manage Job Families' to navigate to task 6. To edit the Job Family, enter the Name into the field 7. To update the job family, click Edit 8. Once the Job Family was updated or corrected, click Done | HCM_ManageJobFamilies_Update_JobFamilies_0034 | 2020-07-06 | 2020-07-06 | 2020-07-06 | 2020-07-06 | Pass | HCM Cloud
14 | HCM | Manage Job Families(Correct) | 1. Login to Oracle Cloud HCM Applications Homepage 2. Click Login 3. Click the Navigator Icon, My Client Groups, Workforce Structures" 4. Click on tasklist icon present on the right side of the application window. 5. Click on task name - 'Manage Job Families' to navigate to task 6. To edit the Job Family, enter the Name into the field 7. To Correct the job family, click Edit 8. Once the Job Family was updated or corrected, click Done | HCM_ManageJobFamilies_Correct_JobFamilies_0035 | 2020-07-07 | 2020-07-07 | 2020-07-07 | 2020-07-07 | Pass | HCM Cloud
15 | HCM | Manage Jobs(Create New Jobs withOut Grades) | 1. Login to Oracle Cloud HCM Applications Homepage 2. Click Login 3. Click the Navigator Icon, My Client Groups, Workforce Structures" 4. Click on task name - 'Manage Jobs’ to navigate to task 5. Click on Create Job 6. Enter Job Description 7. Enter Job Information 8. Click Next 9. Enter Evaluation Criteria 10. Create Profile 11. Click Next 12. Click Submit 13. Click Yes 14. Click OK | HCM_ManageJobs_CreateJobs_WO_Grades_0036 | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-07-08 | Pass | HCM Cloud
16 | HCM | Manage Jobs(Create news Jobs with Create Profiles) | 1. Login to Oracle Cloud HCM Applications Homepage 2. Click Login 3. Click the Navigator Icon, My Client Groups, Workforce Structures" 4. Click on task name - 'Manage Jobs’ to navigate to task 5. Click on Create Job 6. Enter Job Description 7. Enter Job Information 8. Add Valid Grades 9. Click Next 10. Enter Evaluation Criteria 11. Create Profile 12. Click Next 13. Click Submit 14. Click Yes 15. Click OK | HCM_ManageJobs_CreateJobs_CreateProfile_0037 | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-07-09 | Pass | HCM Cloud
17 | HCM | Manage Jobs(Create news Jobs with Add Existing Profile) | 1. Login to Oracle Cloud HCM Applications Homepage 2. Click Login 3. Click the Navigator Icon, My Client Groups, Workforce Structures" 4. Click on task name - 'Manage Jobs’ to navigate to task 5. Click on Create Job 6. Enter Job Description 7. Enter Job Information 8. Add Valid Grades 9. Click Next 10. Enter Evaluation Criteria 11. Add Existing Profile 12. Click Next 13. Click Submit 14. Click Yes 15. Click OK | HCM_ManageJobs_CreateJobs_AddExistingProfile_0038 | 2020-07-12 | 2020-07-12 | 2020-07-12 | 2020-07-12 | Pass | HCM Cloud
18 | HCM | Manage Division( Create a new division option) | 1) Log into Oracle 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Divisions 6) Click Create Icon 7) Select create a new division 8) Enter Division Name, Action Reason, and location 9) To view the Division Details page, click Next->Enter a reporting name into the field->Select Manager from Dropdown list 10) Click Submit 11) Click Yes 12) Click OK 13) Click Search name filed and search the text which just not modified and do validate | HCM_ManageJobs_CreateNewDivision_0039 | 2020-07-13 | 2020-07-13 | 2020-07-13 | 2020-07-13 | Pass | HCM Cloud
19 | HCM | Manage Division( create a new division with an existing organization to define as a division option) | 1) Log into Oracle 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Divisions 6) Click Create Icon 7) Select create an existing organization to define as a division 8) Enter Division Name, Action Reason, and location 9) To view the Division Details page, click Next->Enter a reporting name into the field->Select Manager from Dropdown list 10) Click Submit 11) Click Yes 12) Click OK 13) Click Search name filed and search the text which just not modified and do validate | HCM_ManageJobs_CreateDivision_AnExistingOrganization_0040 | 2020-07-14 | 2020-07-14 | 2020-07-14 | 2020-07-14 | Pass | HCM Cloud
20 | HCM | Manage Division(Edit) | 1) Log into Oracle 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Divisions 6) Search the division name which want to edit 7) Click on Edit option 8) Provide the effective start date and clik OK 9) Edit the Division Name if required(In ths test I did not modify the name field) 10) Click Submit 11) Click Yes 12) Click OK 13) Click Search name filed and search the text which just not modified and do validate | HCM_ManageJobs_EditDivision_UpdateOption_0041 | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-15 | Pass | HCM Cloud