## Sheet1
Sl. No. | Module | Scenarios | Test Cases Steps | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | HCM | Manage Division(Edit with Correct option) | 1) Log into Oracle 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Divisions 6) Search the division name which want to edit 7) Click on Edit option->Choose Correct option 8) Provide the effective start date and clik OK 9) Edit the Division Name if required(Name should be unique. In this test I did not modify the name field) 10) Click Submit 11) Click Yes 12) Click OK 13) Click Search name filed and search the text which just not modified and do validate | HCM_ManageJobs_EditDivision_CorrectOption_0042 | 2020-07-19 | 2020-07-19 | 2020-07-19 | 2020-07-19 | Pass | HCM Cloud
2 | HCM | Manage Departments(Create Department with new dept) | 1) Log into Oracle 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Dept 6) Create Dept 7) Provide the necessary values(refer the TC sheet) 8) Click Submit 9) Click Yes 10) Click OK 11) Click Search name filed and search the text which just not modified and do validate | HCM_ManageDepartments_CreateDepartment_0043 | 2020-07-20 | 2020-07-20 | 2020-07-20 | 2020-07-20 | Pass | HCM Cloud
3 | HCM | Manage Departments(Create Department wth Existing Department) | 1) Log into Oracle 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Dept 6) Create Dept 7) Provide the necessary values(refer the TC sheet) 8) Click Submit 9) Click Yes 10) Click OK 11) Click Search name filed and search the text which just not modified and do validate | HCM_ManageDepartments_Create_ExistingDepartment_0044 | 2020-07-21 | 2020-07-21 | 2020-07-21 | 2020-07-21 | Pass | HCM Cloud
4 | HCM | Manage Departments(Edit Department) | 1) Log into Oracle 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Dept 6) Create Dept 7) Provide the necessary values(refer the TC sheet) 8) Click Submit 9) Click Yes 10) Click OK 11) Click Search name filed and search the text which just not modified and do validate | HCM_ManageDepartments_EditDepartment_0045 | 2020-07-22 | 2020-07-22 | 2020-07-22 | 2020-07-22 | Pass | HCM Cloud
5 | HCM | Manage Grades(Create Grades) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Grades 6) Click on Create button 7) Enter the effective Start Date, Grade Set, Name, Code, Status and click on Next 8) Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the text which just created and do validate 12) LogOut from the applicaton | HCM_Manage Grades_CreateGrade_0046 | 2020-07-23 | 2020-07-23 | 2020-07-23 | 2020-07-23 | Pass | HCM Cloud
6 | HCM | Manage Grades(Negative scenario-Create duplicate Grades) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Grades 6) Click on Create button 7) Enter the effective Start Date, Grade Set, Name, Code, Status 8) Click Submit 9) Validate the error message 10) LogOut from the applicaton | HCM_Manage Grades_CreatedulpicateGrades_0047 | 2020-07-26 | 2020-07-26 | 2020-07-26 | 2020-07-26 | Pass | HCM Cloud
7 | HCM | Manage Grades(Update Grades) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Grades 6) Enter Grade Code and Search 7) Click the edit-> Choose Update option 8) Update the name field-> Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the Grade Code and search again to do validate 12) LogOut from the applicaton | HCM_ManageGrades_EditGrades_0048 | 2020-07-27 | 2020-07-27 | 2020-07-27 | 2020-07-27 | Pass | HCM Cloud
8 | HCM | Manage Grades(Correct Grades) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Grades 6) Enter Grade Code and Search 7) Click the edit-> Choose Correct option 8) Update the name field-> Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the Grade Code and search again to do validate 12) LogOut from the applicaton | HCM_ManageGrades_Edit_CorrectGrades_0049 | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-07-28 | Pass | HCM Cloud
9 | HCM | Manage Grade Rates(Create Grade Rates) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Grades Rates 6) Click on Create button 7) Enter the necessary parameters 8) Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the text which just created and do validate 12) LogOut from the applicaton | HCM_ManageGradeRates_CreateGradeRates_0050 | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-07-29 | Pass | HCM Cloud
10 | HCM | Manage Grade Rates(Negative scenario-Create duplicate Grade Rates) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Grades Rates 6) Click on Create button 7) Enter the necessary parameters 8) Click Submit 9) Error message will encountered | HCM_ManageGradeRates_CreateduplicateGradeRates_0051 | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30 | Pass | HCM Cloud
11 | HCM | Manage Grade Rates(Correct Grade Rates) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Grades Rates 6) Search the previously created Grade Rates 7) Edit using correct option 8) Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the text which just created and do validate 12) LogOut from the applicaton | HCM_ManageGradeRates_UpdateGradeRates_0052 | 2020-08-02 | 2020-08-02 | 2020-08-02 | 2020-08-02 | Pass | HCM Cloud
12 | HCM | Manage Grade Rates(Update Grade Rates) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Grades Rates 6) Search the previously created Grade Rates 7) Edit using Updates option 8) Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the text which just created and do validate 12) LogOut from the applicaton | HCM_ManageGradeRates_CorrectGradeRates_0053 | 2020-08-03 | 2020-08-03 | 2020-08-03 | 2020-08-03 | Pass | HCM Cloud
13 | HCM | Manage Position(CreatePosition wth Create new profile) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Position 6) Click on Create button 7) Enter the necessary parameters along with create new profile 8) Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the text which just created and do validate 12) LogOut from the applicaton | HCM_ManagePosition_CreatePosition_0054 | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2020-08-04 | Pass | HCM Cloud
14 | HCM | Manage Position(CreatePosition wth Create existing profile) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage Position 6) Click on Create button 7) Enter the necessary parameters along with create existing profile 8) Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the text which just created and do validate 12) LogOut from the applicaton | HCM_ManagePosition_CreatePosition_With_ExistingProfile_0055 | 2020-08-05 | 2020-08-05 | 2020-08-05 | 2020-08-05 | Pass | HCM Cloud
15 | HCM | Manage Position(Update Position) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage position 6) Search the previously created position 7) Edit using Updates option 8) Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the text which just created and do validate 12) LogOut from the applicaton | HCM_ManagePosition_UpdatePosition_0056 | 2020-08-06 | 2020-08-06 | 2020-08-06 | 2020-08-06 | Pass | HCM Cloud
16 | HCM | Manage Position(Correct Position) | 1) Log into Oracle Application 2) Click on My Client Groups 3) Click on Workforce Structures 4) Clik on Organizations 5) Click on Manage position 6) Search the previously created position 7) Edit using Correct option 8) Click Submit 9) Click Yes on confirmation message 10) Click OK on confirmation message 11) Click Search name filed and search the text which just created and do validate 12) LogOut from the applicaton | HCM_ManagePosition_CorrectPosition_0057 | 2020-08-09 | 2020-08-09 | 2020-08-09 | 2020-08-09 | Pass | HCM Cloud
17 | HCM | Generate Organization Hierarchy Report | Log into Oracle HCM Cloud Navigate to Navigator Open the report Employee Slection Report Output | HCM_GenerateOrganizationHierarchyReport_0058 | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-08-10 | Pass | HCM Cloud
18 | HCM | Generate Workforce Planning Report | Log into Oracle HCM Cloud Navigate to Navigator Open the report Employee Slection Report Output | HCM_GenerateWorkforcePlanningReport_0059 | 2020-08-11 | 2020-08-11 | 2020-08-11 | 2020-08-11 | Pass | HCM Cloud
19 | HCM | Generate Salary Beyond the Range Report | Log into Oracle HCM Cloud Navigate to Navigator Open the report Employee Slection Report Output | HCM_GenerateSalaryBeyondtheRangeReport_0060 | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-12 | Pass | HCM Cloud
20 | HCM | Generate Missing Department Managers Report | Log into Oracle HCM Cloud Navigate to Navigator Open the report Employee Slection Report Output | HCM_GenerateMissingDepartmentManagersReport_0061 | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | Pass | HCM Cloud