## Sheet1
Sl. No. | Module | Scenarios | Test Cases Steps | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | HCM | Generate Missing Line Managers Report | Login into Oracle HCM Cloud homepage Homepage > OD Reports (tab) Click on the link for the report to see the output. The BI Report displays user selectable parameters (if any). The report will display all the employees along with their previous employment history. | HCM_GenerateMissingLineManagersReport_0062 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 2020-08-18 | Pass | HCM Cloud
2 | HCM | Manage Costing Departments(Create) | Login into Oracle HCM Cloud homepage Homepage > My Client Groups (tab) > Click Manage Costing of Departments (under Payroll) Click on the link for the task to see the Manage Costing of Departments page "Select the department to add costing and click Create Enter the effective date of the costing. Click + (Create) to add new costing detail. "Enter the following details and click Submit 1. Percentage - Usually 100% unless one department cost is split into multiple cost centers 2. Company 3. Division 4. Cost Center 5. Analytical Code" | HCM_ManageCostingDepartments_0063 | 2020-08-19 | 2020-08-19 | 2020-08-19 | 2020-08-19 | Pass | HCM Cloud
3 | HCM | Manage Costing Departments(Update) | Login into Oracle HCM Cloud homepage Homepage > My Client Groups (tab) > Click Manage Costing of Departments (under Payroll) Click on the link for the task to see the Manage Costing of Departments page For existing departments, click Edit > Correct/Update appropriately." Enter the effective date of the costing. Click + (Create) to add new costing detail. "Enter the following details and click Submit 1. Percentage - Usually 100% unless one department cost is split into multiple cost centers 2. Company 3. Division 4. Cost Center 5. Analytical Code" | HCM_Edit_CostingDepartments_0064 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-08-20 | Pass | HCM Cloud
4 | HCM | Manage Costing Departments(Delete) | Login into Oracle HCM Cloud homepage Homepage > My Client Groups (tab) > Click Manage Costing of Departments (under Payroll) Click on the link for the task to see the Manage Costing of Departments page Click delete to delete the department | HCM_Delete_CostingDepartments_0065 | 2020-08-23 | 2020-08-23 | 2020-08-23 | 2020-08-23 | Pass | HCM Cloud
5 | HCM | Manage Costing Departments(Correct) | Login into Oracle HCM Cloud homepage Homepage > My Client Groups (tab) > Click Manage Costing of Departments (under Payroll) Click on the link for the task to see the Manage Costing of Departments page For existing departments, click Edit > Correct/Update appropriately." Enter the effective date of the costing. Click + (Create) to add new costing detail. "Enter the following details and click Submit 1. Percentage - Usually 100% unless one department cost is split into multiple cost centers 2. Company 3. Division 4. Cost Center 5. Analytical Code" | HCM_Correct_CostingDepartments_0066 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | Pass | HCM Cloud
6 | HCM | Update Home Address | Login into Oracle HCM Cloud homepage: Navigation Steps: Homepage > Me > Contact Information 1) Click the "Edit" button 2) Click the "Pencil/Edit" icon above "Home Address" 3) Update existing address 1) Click "Submit" button | HCM_UpdateHomeAddress_0067 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-08-25 | Pass | HCM Cloud
7 | HCM | Family and Emergency Contacts- Add new phone number | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4) In the 'Communications' Tab, Click on 'Edit' to the right of Contacts (upper left) and select "Phone" from the drop-down to add new phone number 5) Enter new or update existing phone "Type" 3) Enter new or update existing phone "Details" - this is the country code - select the country code from the list of values 5) Enter the Area Code 7) Enter the Phone number 8) Click Submit | HCM_ManageContactInfo_Add_Phone_Number_0068 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 2020-08-26 | Pass | HCM Cloud
8 | HCM | Family and Emergency Contacts- Edit existing phone number | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4) In the 'Communications' Tab, Click on 'Edit' to the right of Contacts (upper left) and select "Phone" from the drop-down to add new phone number 5) Enter new or update existing phone "Type" 3) Enter new or update existing phone "Details" - this is the country code - select the country code from the list of values 5) Enter the Area Code 7) Enter the Phone number 8) Click Submit | HCM_ManageContactInfo_Edit_Phone_Number_0069 | 2020-08-27 | 2020-08-27 | 2020-08-27 | 2020-08-27 | Pass | HCM Cloud
9 | HCM | Family and Emergency Contacts- Delete phone number | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4) Click on delete button to delete the phone number | HCM_ManageContactInfo_Delete_Phone_Number_0070 | 2020-08-30 | 2020-08-30 | 2020-08-30 | 2020-08-30 | Pass | HCM Cloud
10 | HCM | Family and Emergency Contacts- Add new email id | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4) Click on Gray Plus (+) to the right of Contacts (upper left) and select "Email" from the drop-down to add new Email 5) Enter new or update existing Email "Type" 6) Enter new or update existing Email "Details" 7) Click on Submit | HCM_ManageContactInfo_Add_Email_0071 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | Pass | HCM Cloud
11 | HCM | Family and Emergency Contacts- Edit email id | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4) Click on Gray Plus (+) to the right of Contacts (upper left) and select "Email" from the drop-down to add new Email 5) Enter new or update existing Email "Type" 6) Enter new or update existing Email "Details" 7) Click on Submit | HCM_ManageContactInfo_Edit_Email_0072 | 2020-09-01 | 2020-09-01 | 2020-09-01 | 2020-09-01 | Pass | HCM Cloud
12 | HCM | Family and Emergency Contacts-Delete email id | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4)Click on delete button to delete emal | HCM_ManageContactInfo_Delete_Email_0073 | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2020-09-02 | Pass | HCM Cloud
13 | HCM | Family and Emergency Contacts- Add new Address | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4) Click on the Gray Plus (+) next to Address to add a new address 5) Select Address "Type" 6) Enter Address details as necessary Note: Asterisk ( * ) indicates fields that are required 7) Clik on submit button | HCM_ManageContactInfo_Add_Address_0074 | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-03 | Pass | HCM Cloud
14 | HCM | Family and Emergency Contacts- edit existing Address | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4)Edit the existing address 5) Select Address "Type" 6) Enter Address details as necessary Note: Asterisk ( * ) indicates fields that are required 7) Clik on submit button | HCM_ManageContactInfo_Edit_Address_0075 | 2020-09-06 | 2020-09-06 | 2020-09-06 | 2020-09-06 | Pass | HCM Cloud
15 | HCM | Family and Emergency Contacts- delete existing Address | 1)Login into Oracle HCM Cloud homepage 2)Homepage > Me > Family and Emergency Contacts 3)Click on "Edit" button 4) Click on delete button to delete the existing address | HCM_ManageContactInfo_Delete_Address_0076 | 2020-09-07 | 2020-09-07 | 2020-09-07 | 2020-09-07 | Pass | HCM Cloud
16 | HCM | Manage Document Records(Add document Record) | Login into Oracle HCM Cloud homepage Homepage > Me > Document Records Click on "Add" button Select the appropriate Document Type Exit Interview Questionnaire - Part 1 Provide all the required information as appropriate, based on the form selected. Click "Submit" | HCM_ManageDocumentRecords_Add_Record_0077 | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | Pass | HCM Cloud
17 | HCM | Manage Document Records(title verification) | Login into Oracle HCM Cloud homepage Homepage > Me > Document Records Verify page title | HCM_ManageDocumentRecords_VerifyPageTitle_0078 | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2020-09-09 | Pass | HCM Cloud
18 | HCM | Manage Document Records(Edit document Record) | Login into Oracle HCM Cloud homepage Homepage > Me > Document Records Click on "Edit" button Select the appropriate Document Type Exit Interview Questionnaire - Part 1 Provide all the required information as appropriate, based on the form selected. Click "Submit" | HCM_ManageDocumentRecords_Edit_Record_0079 | 2020-09-10 | 2020-09-10 | 2020-09-10 | 2020-09-10 | Pass | HCM Cloud
19 | HCM | Manage Contact Info(Family and EmergencyContact title verification) | Login into Oracle HCM Cloud homepage Homepage > Me > Personal Information-> Family and Emergency Contact Verify page title | HCM_ManageContactInfo_VerifyPageTitle_0080 | 2020-09-13 | 2020-09-13 | 2020-09-13 | 2020-09-13 | Pass | HCM Cloud
20 | HCM | Manage Document Records(Delete document Record) | Login into Oracle HCM Cloud homepage Homepage > Me > Document Records Click on "Edit" button Clck the delete button verify the details | HCM_ManageDocumentRecords_Delete_Record_0081 | 2020-09-14 | 2020-09-14 | 2020-09-14 | 2020-09-14 | Pass | HCM Cloud