## Sheet1
Sl. No. | Module | Scenarios | Test Cases Steps | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | HCM | Add Phone Number of an employee using Contact Info | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Add Phone Number-> 4) Click the '(+) Add' button next to "Communications" and select "Phone" from the drop down 5) Update existing phone "Type" 6) Update existing "Country Code" - select the country code from the list of values 7) Update existing "Area Code" 8) Update existing "Number" 9) click Submit 10) Capture the confirmation notification 11) Capture the group it is pending with for approval | HCM_ContactInfo_AddPhone_0082 | 2020-09-20 | 2020-09-20 | 2020-09-20 | 2020-09-20 | Pass | HCM Cloud
2 | HCM | Edit Phone Number of an employee using Contact Info | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Edit Phone Number-> 4) Click the Edit button - upper right 5) Update existing phone "Type" 6) Update existing "Country Code" - select the country code from the list of values 7) Update existing "Area Code" 8) Update existing "Number" 9) click Submit 10) Capture the confirmation notification 11) Capture the group it is pending with for approval | HCM_ContactInfo_EditPhone_0083 | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2020-09-21 | Pass | HCM Cloud
3 | HCM | Delete Phone Number of an employee using Contact Info | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Delete Phone Number-> 4) Click the Edit button - upper right 5) click Delete Button 6) Capture the confirmation notification 7) Capture the group it is pending with for approval | HCM_ContactInfo_DeletePhone_0084 | 2020-09-22 | 2020-09-22 | 2020-09-22 | 2020-09-22 | Pass | HCM Cloud
4 | HCM | Add Email address of an employee using Contact info | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Add/Edit Email Address-> 4) Click Add and select Email Address to add a new email 5) If the email is to be corrected, click the Edit pencil icon. 6) Enter the email type and the address. 7) click Submit 8) Capture the confirmation notification 9) Capture the group it is pending with for approval | HCM_ContactInfo_Add_Email_0085 | 2020-09-23 | 2020-09-23 | 2020-09-23 | 2020-09-23 | Pass | HCM Cloud
5 | HCM | Edit Email address of an employee using Contact info | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Edit Email Address-> 4) Click pencile icon for edit and update the element 5) click Submit 6) Capture the confirmation notification 7) Capture the group it is pending with for approval | HCM_ContactInfo_Edit_Email_0086 | 2020-09-24 | 2020-09-24 | 2020-09-24 | 2020-09-24 | Pass | HCM Cloud
6 | HCM | Delete Email address of an employee using Contact info | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Delete Email --> 4) Click pencile icon for edit and update the element 5) click Delete 6) Capture the confirmation notification 7) Capture the group it is pending with for approval | HCM_ContactInfo_Delete_Email_0087 | 2020-09-27 | 2020-09-27 | 2020-09-27 | 2020-09-27 | Pass | HCM Cloud
7 | HCM | Modify Existing Emergency Contact Start Date | Clik on My Client Group Click on Person Managment Provide Name and Personal Number Click on Search Button Clik on Search Results Click on task icon Clik on "Person" from Personal and Managment Clik on Contact link Provide the Change Start Date Click OK->Yes->OK Click on task icon Clik on "Person" from Personal and Managment Clik on Contact link Click OK | HCM_ModifyExistingEmergencyContact_StartDateChange_0088 | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-09-28 | Pass | HCM Cloud
8 | HCM | Action Label Changed for Employment Flows on Contingent Worker | Login into Oracle HCM Cloud homepage My client Group-> Click on Add Contingent Worker validate "Instead of Action and Action Reason you will be able to see the Action as" What's the way to add a contingent worker?" and Action Reason as "Why are you adding a contingent worker?"" | HCM_ActionLabelChanged_EmploymentFlows_Contingent_Worker_0089 | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2020-09-29 | Pass | HCM Cloud
9 | HCM | Action Label Changed for Employment Flows on Pending Worker | Login into Oracle HCM Cloud homepage My Client group-> Add an Pending Worker You will be able to see the Action as "What's the way to add the pending worker?" and Action Reason as " Why are you adding a pending worker?" | HCM_ActionLabelChanged_EmploymentFlows_Add_Pending Worker_0090 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-09-30 | Pass | HCM Cloud
10 | HCM | Action Label Changed for Employment Flows on non Worker | Login into Oracle HCM Cloud homepage My Client group-> Add an Non Worker You will be able to see the Action as "What's the way to add the a non worker?" and Action Reason as " Why are you adding a non worker?" | HCM_ActionLabelChanged_EmploymentFlows_Add_Non_Worker_0091 | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 | Pass | HCM Cloud
11 | HCM | Configure Checklist and Task Display Properties avalidation | Login into Oracle HCM Cloud homepage My Client group-> Quick Actions(Show more)-> Employment-> Checklist Template Open any of the Checklist Go to the Task Tab Open any of the Tasks | HCM_ConfigureChecklist_TaskDisplayProperties_0092 | 2020-10-04 | 2020-10-04 | 2020-10-04 | 2020-10-04 | Pass | HCM Cloud
12 | HCM | Sequence Checklist Tasks | Login into Oracle HCM Cloud homepage My Client group-> Quick Actions(Show more)-> Employment-> Checklist Template Open any of the Checklist Go to the Task Tab Open any of the Tasks | HCM_SequenceChecklist_Tasks_0093 | 2020-10-05 | 2020-10-05 | 2020-10-05 | 2020-10-05 | Pass | HCM Cloud
13 | HCM | Display all transaction related to checklis | Login into oracle Application Tools-> Transaction Console Click on Transaction Summary In Search type "Checklist"->enter --Validation--- All the checklist related transaction is dispalyed with the status | HCM_ImprovedChecklistTransaction_0094 | 2020-10-06 | 2020-10-06 | 2020-10-06 | 2020-10-06 | Pass | HCM Cloud
14 | HCM | Management Hierarchy | Login into oracle Application Tools-> Transaction Console Click on Approval Rules In Search, type any Rule(Resignation) Click on Hierracrch Tab from the rule Validation The Management Hierarchy will be displayed at the bottom of the page Two radio buttons should be visible 1. Use primary assignment hierarchy 2. User Current assignment hierarchy | HCM_RouteEmploymentApprovals_0095 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 2020-10-07 | Pass | HCM Cloud
15 | HCM | Landing page Validation | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information Validate the landing page | HCM_ContactInfoPage_TitleValidation_0096 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 2020-10-08 | Pass | HCM Cloud
16 | HCM | Create a New Address of an employee | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Add New Address-> 4) Click the '(+) Add' button next to "Communications" and select "Phone" from the drop down 5) Update existing phone "Type" 6) Update existing "Country Code" - select the country code from the list of values 7) Update existing "Area Code" 8) Update existing "Number" 9) click Submit 10) Capture the confirmation notification 11) Capture the group it is pending with for approval | HCM_CreateNewAddress_Employee_0097 | 2020-10-09 | 2020-10-09 | 2020-10-09 | 2020-10-09 | Pass | HCM Cloud
17 | HCM | Edit a New Address of an employee | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Edit New Address-> 4) Click on edit pencile icon 5) update teh necessary changes 6) click Submit 7) Capture the confirmation notification 8) Capture the group it is pending with for approval | HCM_Edit_NewAddress_Employee_0098 | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-13 | Pass | HCM Cloud
18 | HCM | Delete a New Address of an employee | 1)Log into Oracle HCM Cloud 2)Homepage > Me > Personal Details > Contact Information 3) <--Add New Address-> 4) Click the '(+) Add' button next to "Communications" and select "Phone" from the drop down 5) Update existing phone "Type" 6) Update existing "Country Code" - select the country code from the list of values 7) Update existing "Area Code" 8) Update existing "Number" 9) click Submit 10) Capture the confirmation notification 11) Capture the group it is pending with for approval | HCM_Delete_NewAddress_Employee_0099 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | Pass | HCM Cloud
19 | HCM | Change Personal Details - Name | Login into Oracle HCM Cloud homepage Homepage > Me > Personal Details Click the "Edit" button in the "Name" area of the page Update Name details as necessary Click on Submit capture the confirmation message | HCM_ChangePersonalDetails_Name_0100 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 | Pass | HCM Cloud
20 | HCM | Personal detals page title validation | Login into Oracle HCM Cloud homepage Homepage > Me > Personal Details Click the "Edit" button in the "Name" area of the page Update Name details as necessary Click on Submit | HCM_PersonalDetailsPageTitleValdation_0101 | 2020-10-16 | 2020-10-16 | 2020-10-16 | 2020-10-16 | Pass | HCM Cloud