## Sheet1
Sl. No. | Module | Scenarios | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | Purchasing | Return list of PreApproved requisition details from requisition summary page | PR_RequisitionInPreApprovedSearch_0024 | 2019-11-18 | 2019-11-18 | 2019-11-18 | 2019-11-18 | Pass | Dev instance
2 | Purchasing | Return list of Returned requisition details from requisition summary page | PR_RequisitionReturnedSearch_0025 | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-11-19 | Pass | Dev instance
3 | Purchasing | Verify the charge account fund details on edit PR | PR_ChkFund_ChrgAcct_MoreInfoPR_0026 | 2019-11-20 | 2019-11-20 | 2019-11-20 | 2019-11-20 | Pass | Dev instance
4 | Purchasing | Add multiple charge account on a PR which is unique one | PR_Add_Unique_Multi_ChrgAcct_AddOnMoreInfoPR_0027 | 2019-11-21 | 2019-11-21 | 2019-11-21 | 2019-11-21 | Pass | Dev instance
5 | Purchasing | Trying to add duplicate charge account on edit PR | PR_Add_Duplicate_Multi_ChrgAcct_OnMoreInfoPR_0028 | 2019-11-24 | 2019-11-24 | 2019-11-24 | 2019-11-24 | Pass | Dev instance
6 | Purchasing | Change the GLDate from date value to Multiple value on edit PR | PR_GLDateChangesToMultiple_0029 | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2019-11-25 | Pass | Dev instance
7 | Purchasing | Validate the Shopping Cart link navigation flow | PR_ShoppingCartLinkValidation_0030 | 2019-11-26 | 2019-11-26 | 2019-11-26 | 2019-11-26 | Pass | Dev instance
8 | Purchasing | Edit and submit the PR with Edit Line Lines on "Deliver-To Location" as "Location" | PR_EditPR_EditLine_DeliverToLocation_ByLocation_0031 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | Pass | Edit PR - Login with BRAHMEG user 1) select more info PR 2) Edit PR 3) Approver Checkout 4) Edit Lines 5) Deliver-To Location with Location as "Location" 6) Submit the request 7) Confirm message will displayed and capture the page.
9 | Purchasing | Edit and submit the PR with Edit Line Lines on "Deliver-To Location" as "Organization" | PR_EditPR_EditLineDeliverToLocationByOrganization_0032 | 2019-11-28 | 2019-11-28 | 2019-11-28 | 2019-11-28 | Pass | Edit PR - Login with BRAHMEG user 1) select more info PR 2) Edit PR 3) Approver Checkout 4) Edit Lines 5) Deliver-To Location with Location as "Organization" 6) Submit the request 7) Confirm message will displayed and capture the page.
10 | Purchasing | Edit and submit the PR with Need By Date as past date | PR_EditPR_AsPastNeedByDate_0033 | 2019-12-01 | 2019-12-01 | 2019-12-01 | 2019-12-01 | Pass | Edit PR - Login with BRAHMEG user 1) select more info PR * 2) Edit PR * 3) Approver Checkout * 4) Edit Need By Date with past date * 5) Submit the request * 7) Error message will displayed and capture the page.
11 | Purchasing | Insert the Approver name from ManageApprovals option on Edit PR | PR_ManageApprovals_InsertApprovarByName_0034 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-02 | Pass | Dev instance
12 | Purchasing | Insert the duplicate Approver name from ManageApprovalsoption on Edit PR | PR_ManageApprovals_InsertduplicateApprovarByName_0035 | 2019-12-03 | 2019-12-03 | 2019-12-03 | 2019-12-03 | Pass | Dev instance
13 | Purchasing | Delete the Approver name from ManageApprovalsoption on Edit PR | PR_ManageApprovals_DeleteApprover_0036 | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2019-12-04 | Pass | Dev instance
14 | Purchasing | Using Email id insert the Approver name from ManageApprovalsoption on Edit PR | PR_ManageApprovals_InsertApprovarByEmail_0037 | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2019-12-05 | Pass | Dev instance
15 | Purchasing | Delete and validate the Item from shopping cart | PR_DeleteItemFRMApproverShoppingCart_0038 | 2019-12-08 | 2019-12-08 | 2019-12-08 | 2019-12-08 | Pass | Dev instance
16 | Purchasing | Validate the navigation flow on "PR Details" link on selected PR | PR_OpePRDetailsLinkValidation_0039 | 2019-12-09 | 2019-12-09 | 2019-12-09 | 2019-12-09 | Pass | Dev instance
17 | Purchasing | Copy the requisition to the existing requisition using "Copy To Cart" option | PR_Requisition_CopyToCart_AddToCart_0040 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | Pass | Dev instance
18 | Purchasing | Copy the requisition to the existing requisition using "New To Cart" option | PR_Requisition_CopyToCart_NewCart_0041 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | Pass | Dev instance
19 | Purchasing | Search the requisition which is created in 7days | PR_Search7daysCreatedRequisition_0042 | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-12 | Pass | Dev instance
20 | Purchasing | Validate the home page title of Oracle Applications | PR_VerifyHomePageTitle_0043 | 2019-12-16 | 2019-12-16 | 2019-12-16 | 2019-12-16 | Pass | Dev instance