## Sheet1
Sl. No. | Module | Scenarios | Test Cases Steps | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | Purchasing | Checking the last 30 days PR details from Requisition search page | 1) Login the application 2)Edit the PR 3)Click on Requisition Tab 4)Click on Search Button 5)Choose Requisition Created as "Last 30 Days" and Requisition Status as "Any Time" 6) Click on Go 7)Take the screen shot 8)Log out the application 9)Close the application | PR_SearchLast30DaysCreatedRequisition_0044 | 2019-12-18 | 2019-12-18 | 2019-12-18 | 2019-12-18 | Pass | Dev instance
2 | Purchasing | Checking the last 60 days PR details from Requisition search page | 1) Login the application 2)Edit the PR 3)Click on Requisition Tab 4)Click on Search Button 5)Choose Requisition Created as "Last 60 Days" and Requisition Status as "Any Time" 6) Click on Go 7)Take the screen shot 8)Log out the application 9)Close the application | PR_SearchLast60DaysCreatedRequisition_0045 | 2019-12-19 | 2019-12-19 | 2019-12-19 | 2019-12-19 | Pass | Dev instance
3 | Purchasing | Checking the last 60 days Cancelled PR details from Requisition search page | 1) Login the application 2)Edit the PR 3)Click on Requisition Tab 4)Click on Search Button 5)Choose Requisition Created as "Last 60 Days" and Requisition Status as "Cancelled" 6) Click on Go 7)Take the screen shot 8)Log out the application 9)Close the application | PR_SearchCancelledRequisitionOnlyInLast60Days_0046 | 2019-12-22 | 2019-12-22 | 2019-12-22 | 2019-12-22 | Pass | Dev instance
4 | Purchasing | Checking the Any Time Rejected PR details from Requisition search page | 1) Login the application 2)Edit the PR 3)Click on Requisition Tab 4)Click on Search Button 5)Choose Requisition Created as "Any Time" and Requisition Status as "Rejected" 6) Click on Go 7)Take the screen shot 8)Log out the application 9)Close the application | PR_SearchRejectedRequisitionOnlyAtAnyTimesAsCreationDate_0047 | 2019-12-23 | 2019-12-23 | 2019-12-23 | 2019-12-23 | Pass | Dev instance
5 | Purchasing | Search the Inprocess PRs and add item to cart using Coy to Cart option then delete it from the cart | 1) Edit the PR 2) Go to Requisition Tab 3) Search the In Process PR 4) Select any PR and try to copy the whole items to existing PR 5) Submit the request 6) Take the screan shot of the new added item 7) Delete it from the existing cart and then submit th erequest 8) LogOut | PR_SearchInProcessPR_CopyToCart_AddTocart_DeleteFrmCart_0048 | 2019-12-24 | 2019-12-24 | 2019-12-24 | 2019-12-24 | Pass | Dev instance
6 | Purchasing | Search the Cancelled PRs and add item to cart using "Copy to Cart" option then delete it from the cart | 1) Login the application and Edit the PR 2) Go to Requisition Tab 3) Search the Cancelled PR 4) Select any PR and try to copy the whole items to existing PR 5) Submit the request 6) Take the screan shot of the new added item 7) Delete it from the existing cart and then submit the request 8) LogOut | PR_SearchCancelledPR_CopyToCart_AddTocart_DeleteFrmCart_0049 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | Pass | Dev instance
7 | Purchasing | Cancell the already cancelled PR(Negative scenario) | 1) Login the application Edit the PR 2) Go to Requisition Tab 3) Search the Cancelled PR 4) Select any PR and try to cancell it once again 5) expected to encountered error. 6) Validate the error msg 7) LogOut | PR_CancelRequisitionOnCanceledPR_N_0050 | 2019-12-26 | 2019-12-26 | 2019-12-26 | 2019-12-26 | Pass | Dev instance
8 | Purchasing | Change the already cancelled PR(Negative scenario) | 1) Edit the PR 2) Go to Requisition Tab 3) Search the Cancelled PR 4) Select any PR and try to change 5) expected to encountered error. 6) Validate the error msg 7) LogOut | PR_Change_CancelledRequisition_N_0051 | 2019-12-29 | 2019-12-29 | 2019-12-29 | 2019-12-29 | Pass | Dev instance
9 | Purchasing | Validate the error message if you will perform any action without selecting any PR | 1) Edit the PR 2) Go to Requisition Tab 3) Search the Cancelled PR 4) Do not select any PR and try to change 5) expected to encountered error. 6) Validate the error msg 7) LogOut | PR_ValidateErrorMSGIfPRnotSelectedAndtryingToDoActionAnything_N_0052 | 2019-12-30 | 2019-12-30 | 2019-12-30 | 2019-12-30 | Pass | Dev instance
10 | Purchasing | Validate the Oracle iProcurement: Checkout page title | 1)Log in with valid UID and PWD 2) Edit the Need More Info PR 3) Go to Requisition Tab 4) Validate the Oracle iProcurement: Checkout page title 5) LogOut | PR_VerifyiProcurementPageTitle_0053 | 2019-12-31 | 2019-12-31 | 2019-12-31 | 2019-12-31 | Pass | Dev instance
11 | Purchasing | Validate the landing page title "Notification Details" | 1)Log in with UID and PWD 2) Select the required PR 3) Now the landing page would be Notification Details, hence validate the page title 4) LogOut from the application | PR_VerifyNotificationLandingPageTitle_0054 | 2020-01-01 | 2020-01-01 | 2020-01-01 | 2020-01-01 | Pass | Dev instance
12 | Purchasing | Partially cancel the PR | 1)Create the PR 2)Send it to approval 3)From the approver, select Need more Info and send it back to the orizinator id 4)Edit the PR 5)Approver Checkout->Edit Line->Select the Line->Click copy->Apply->Submit->Continue->Edit PR->Requisition Tab->Select the PR and click cancel->continue->Select the check box->Continue->Submit 6) PR cancelled and no where it is showing 7) LogOut from th eapplication | PR_PartiallyCancelPR_0055 | 2020-01-02 | 2020-01-02 | 2020-01-02 | 2020-01-02 | Pass | Dev instance
13 | Purchasing | Cancel the entire PR | 1)Create the PR 2)Send it to approval 3)From the approver, select Need more Info and send it back to the orizinator id 4)Edit the PR 5)Requisition Tab->Select the PR and click cancel->Click on "Cancel Entire Requsition"->Submit 6) PR cancelled and no where it is showing 7) LogOut from th eapplication | PR_CancelEntirePR_0056 | 2020-01-05 | 2020-01-05 | 2020-01-05 | 2020-01-06 | Pass | Dev instance
14 | Purchasing | Cancel button return back return back to the original page | 1)Login with valid UID/PWD 2)Edit the PR 3)Requisition Tab->Select the PR and click cancel->Click on "Cancel" Button-> 4)Page re-direct to it's original position 7) LogOut from the application | PR_CancelTransactionAndReturnBackToOriginalSearch_0057 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 2020-01-07 | Pass | Dev instance
15 | Purchasing | Landing Page title validation | 1)Login with valid UID/PWD 2)Edit the PR 3)Requisition Tab->Select the PR and click cancel->Click on "Cancel" Button-> 4)Page re-direct to it's original position 7) LogOut from the application | PR_CancelPageTitleVerification_0058 | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-08 | Pass | Dev instance
16 | Purchasing | complete requisitions with incomplete status | 1)Login with valid UID/PWD 2)Edit the PR 3)Requisition Tab->Select theIn Process PR and click Complete Button 4) LogOut from the application | PR_CompleteRequisitionsInprocessData_0059 | 2020-01-08 | 2020-01-08 | 2020-01-08 | 2020-01-09 | Pass | Dev instance
17 | Purchasing | Searching the Incomplete PR from Edit PR | 1) Login the application 2)Edit the PR 3)Click on Requisition Tab 4)Click on Search Button 5)Choose Requisition Created as Any Time and Requisition Status as Incomplete 6) Take the screen shot 7)Log out the application 8)Close the application | PR_SearchAnyTimeIncompleteStatusesPR_0060 | 2020-01-09 | 2020-01-09 | 2020-01-09 | 2020-01-10 | Pass | Dev instance
18 | Purchasing | Complete the Incomplete requisition | 1) Login the application 2)Edit the PR 3)Click on Requisition Tab 4)Click on Search Button 5)Choose Requisition Created as Any Time and Requisition Status as Incomplete 6) Select and open the PR 7) Click on change button 8) Click on Yes->Checkout->Submit Button 9) Log out the application 10)Close the application | PR_CompleteTheIncompletePR_0061 | 2020-01-12 | 2020-01-12 | 2020-01-12 | 2020-01-13 | Pass | Dev instance
19 | Purchasing | Verify the chnaged status from "Incompelete" to "Inprocess" | 1) Login the application 2)Edit the PR 3)Click on Requisition Tab 4)Click on Search Button 5)Choose Requisition Created as Any Time and Requisition Status as Incomplete 6) Select and open the PR 7) Click on change button 8) Click on Yes->Checkout->Submit Button 9)Verify the changed PR as Inprocess (Incomplete changes from Inprocess) 10) Log out the application 11)Close the application | PR_Verify_Inproces_As_Status_AfterChanged_FRM_IncompeletePR_0062 | 2020-01-13 | 2020-01-13 | 2020-01-13 | 2020-01-14 | Pass | Dev instance
20 | Purchasing | lear Button functionality on Requisitions Search page | 1) Login the application 2)Edit the PR 3)Click on Requisition Tab 4)Click on Search Button 5)Choose Requisition Created as Any Time and Requisition Status as Incomplete 6) Take the screen shot 7)Click on Clear button and take screen shot 8)Log out the application 9)Close the application | PR_ClearButtonTestFunctionlity_0063 | 2020-01-14 | 2020-01-14 | 2020-01-14 | 2020-01-16 | Pass | Dev instance