## Sheet1
Sl. No. | Module | Scenarios | Test Cases Steps | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | Purchasing | Purchase Order Creation without Approval | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders 3)Provides all required inputs 4)Click Submit button to generate the PO 5)Log out from the application 6)Close the browser | PO_BlanketCreationWOApproval_0084 | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-02-18 | Pass | Dev instance
2 | Purchasing | Purchase Order Creation and send it to the approver for approval | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders 3)Provides all required inputs 4)Click Submit button to generate the PO 5)Clcik Approve button to send it to approver-> Now it will go to the approver 6)Log out from the application 7)Close the browser | PO_BlanketCreationAndSentToApproverForApproval_0085 | 2020-02-19 | 2020-02-19 | 2020-02-19 | 2020-02-19 | Pass | Dev instance
3 | Purchasing | Find out the approver details of the particular PO | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Provides the PO Number 4)Click Submit button 5)Check the approver name with whom PO is pending with for approval. Using Inquire¦View Action History option 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_BlanketCreationAndVerifyApproverDetails_0086 | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-20 | Pass | Dev instance
4 | Purchasing | Find out the status and approver details for a given PO | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Provides the PO Number 4)Click Submit button 5)Check the Status of the PO and the approver name for a given PO 6)Take a Screen shot 7)Log out from the application 8)Close the browser" | PO_FindOutPOStatusOfGivenPO_0087 | 2020-02-23 | 2020-02-23 | 2020-02-23 | 2020-02-23 | Pass | Dev instance
5 | Purchasing | To get all type of PO status, we will do blank search | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Do not provides any PO Number and make sure that the PO field should blank. 4)Click Submit button 5)Check the Status of the PO and the approver name for a given PO - This step is not required for this scenario 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_BlankPOSearch_0088 | 2020-02-24 | 2020-02-24 | 2020-02-24 | 2020-02-24 | Pass | Dev instance
6 | Purchasing | Search the list of POs which havinf approve only status | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on Status Tab and choose the Approve from the drop down 4)Click Find button 5)Take a Screen shot 6)Log out from the application 7)Close the browser" | PO_Search_ApprovedPOSearch_0089 | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-02-25 | Pass | Dev instance
7 | Purchasing | Search the list of POs which havinf approved only status | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on Status Tab and choose the In Process status from the drop down 4)Click Find button 5)Take a Screen shot 6)Log out from the application 7)Close the browser | PO_Search_InProcessPOSearch_0090 | 2020-02-26 | 2020-02-26 | 2020-02-26 | 2020-02-26 | Pass | Dev instance
8 | Purchasing | Retrive a list of PO withing specific date | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on "Date Ranges" Tab and provides To and From date 4)Click Find button 5)Take a Screen shot 6)Log out from the application 7)Close the browser | PO_Search_SpecificDateRange_0091 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 | Pass | Dev instance
9 | Purchasing | Error message valifation if the search date is mis-mathced. | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on "Date Ranges" Tab and provides dates. From date must be greter than To date 4)Click Find button -> Error Popup expecting 5)Take a Screen shot 6)Log out from the application 7)Close the browser */ | PO_Search_ErrorMSGValidationOnDateRangeMismatch_0092 | 2020-03-01 | 2020-03-01 | 2020-03-01 | 2020-03-01 | Pass | Dev instance
10 | Purchasing | Error message valifation if the the particular search criteria fail w.r.t PO status(e.g- Approved, In Process etc.) | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on "Date Ranges" Tab and provides proper dates 4)Click on status Tab and choose Approved as status 5)Click Find button -> Error Popup expecting 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_ErrorMSGValidationIfStatusPONotFound_0093 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 2020-03-02 | Pass | Dev instance
11 | Purchasing | Retrive the list of POs which status is Approved and in a specfic range | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on "Date Ranges" Tab and provides proper dates 4)Click on status Tab and choose Approved as status 5)Click Find button -> and Validate the Approved status POs 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_ApprovedStatusPOWithinSpecificDateRange_0094 | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-03-03 | Pass | Dev instance
12 | Purchasing | Retrive the list of POs which status is In Process and in a specfic range | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on "Date Ranges" Tab and provides proper dates 4)Click on status Tab and choose In Process as status 5)Click Find button -> and Validate the In Process status POs 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_InProcessPOStatusWithinSpecificDateRange_0095 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-03-04 | Pass | Dev instance
13 | Purchasing | Searching the PO using the contract id | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on "Related Documents" Tab and provides the contract Id 4)Click Find button 5) Open the contract id and take the screen shot 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_UsingContractID_0096 | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-03-05 | Pass | Dev instance
14 | Purchasing | Get the PO details using Line SupplierItemID | 1) Login the application 2)Navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Under the Line Tab provide the Supplier Item Id 4)Click Find button 5)Get the PO number and click on open button 6)Get the status and -> Take a Screen shot 7)Log out from the application 8)Close the browser" | PO_Search_FindPODetails_UsingLine_SupplierItemID_0097 | 2020-03-08 | 2020-03-08 | 2020-03-08 | 2020-03-08 | Pass | Dev instance
15 | Purchasing | Get the PO details using Line LocationId | 1) Login the application 2)Navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on Deliver to Tab and provide the Location Id 4)Click Find button 5)Get the PO number 6)Get the status and -> Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_FindPODetails_UsingLocationId_0098 | 2020-03-09 | 2020-03-09 | 2020-03-09 | 2020-03-09 | Pass | Dev instance
16 | Purchasing | Get the PO details using Line Account Period dates | 1) Login the application 2)Navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on Accounts Tab provide the From and To period dates along with chanrge code 4)Click Find button 5)Get the PO an dcharge code 6)Take a Screen shot 7)Log out from the application 8)Close the browser" | PO_Search_FindPODetails_UsingSpecificAccountingDates_0099 | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 | Pass | Dev instance
17 | Purchasing | Get the PO details using ChargeCode | 1) Login the application 2)Navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on Accounts Tab provide the charge code 4)Click Find button 5)Get the PO and charge code 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_FindPODetails_UsingChargeCode_00100 | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-03-11 | Pass | Dev instance
18 | Purchasing | Get the PO details using Line-> Account Period dates along with Charge code(combination of accounts dates and charge code) | 1) Login the application 2)Navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on Accounts Tab provide the From and To period dates along with charge code 4)Click Find button 5)Get the PO and charge code 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_FindPODetails_WithinDateRangeWithChargeCode_00101 | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-03-12 | Pass | Dev instance
19 | Purchasing | Get the PO details using Invoice Number | 1) Login the application 2)Navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on Related Documents Taband enter Invoice Number 4)Click Find button 5)Get the PO and atatus of the PO from the Invoice number and print in th console 6)Take a Screen shot 7)Log out from the application 8)Close the browser" | PO_Search_FindPODetailsUsing_Invoice_Number_00102 | 2020-03-15 | 2020-03-15 | 2020-03-15 | 2020-03-15 | Pass | Dev instance
20 | Purchasing | Get the PO details using Receipt Number | 1) Login the application 2)Navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders->Purchase_Orders_Summary 3)Click on Related Documents Tab and enter Receipt Number 4)Click Find button 5)Get the PO and atatus of the PO from the Receipt number and print in th console 6)Take a Screen shot 7)Log out from the application 8)Close the browser | PO_Search_FindPODetailsUsing_Receipt_Number_00103 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 2020-03-16 | Pass | Dev instance