## Sheet1
Sl. No. | Module | Scenarios | Test Cases Steps | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | Purchasing | Standard PO creation from PR | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> AutoCreate 4) Clear Buyer Name->Provide the approved PR number(If you do not have the PR handy- do the blank search on that page, and you will get the lict of approved PR, choose anyone.) 5) Click Find 6) Select the Requisition Line -> Automatic 7) rovide Supplier name and site details-> Click Create-> po will generate 8) Click Terms->Prvide Inco Term, Carrier,Inco Location,address 9)Enter Ship to and Bill to 10) Header DFF 11) enter Sourcing Method-> ok 12) Click on Approve button.-> it will go to next user to approve the PO. * 13) LogOut and Close the browser. | PO_StandarePOCreationFromPR_00104 | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2020-03-18 | Pass | Dev instance
2 | Purchasing | Standared PO Creation Without PR | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> Purchase_Order->Purchase_Orders 4) Provide inputs on Supplier Name,site, and contact field 5) Click on Terms Tab and provide Inco Term – DDP 6) Click on po Header-> provides input of iscount Note, amount and currency filed 7) Enter the Item number, price, Promised Date, Need By Date, 8) Click Shipment-> Enter ORG and Ship to 9) Click on Save button-> Take the PO numer 10) Click on Approve button.-> it will go to next user to approve the PO. 11) LogOut and Close the browser. | PO_StandarePOCreation_WO_PR_00105 | 2020-03-19 | 2020-03-19 | 2020-03-19 | 2020-03-19 | Pass | Dev instance
3 | Purchasing | Error PopUp encountered while provide incorrect PromiseDate | 1) Open the Browser * 2) Login with correct user * 3) Click on MWSPC_PURCHASING_SUPERUSE-> AutoCreate * 4) Clear Buyer Name->Provide the approved PR number(If you do not have the PR handy- do the blank search on that page, and you will get the lict of approved PR, choose anyone.) * 5) Click Find 6) Select the Requisition Line -> Automatic 7) Provide Supplier name and site details-> Click Create-> po will generate 8) Click Terms->Prvide Inco Term, Carrier,Inco Location,address 9)Enter Ship to and Bill to 10) Header DFF 11) enter Sourcing Method-> ok 12) Click on Approve button.-> Error encountered saying Promise date should be higer date-> Click Cancel-> provide correct date->Click Approve button agan->it will go to next user to approve the PO. 13) LogOut and Close the browser. | PO_ErroValidationOnIncorrectPromiseDate_00106 | 2020-03-22 | 2020-03-22 | 2020-03-22 | 2020-03-22 | Pass | Dev instance
4 | Purchasing | Find Approved PR From AutoCreate Option | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> AutoCreate 4) Approved Status as Yes and click find-> Take Screen shot 5) LogOut and Close the browser. | PO_FindApprovedPRFromAutoCreateOption_00107 | 2020-03-23 | 2020-03-23 | 2020-03-23 | 2020-03-23 | Pass | Dev instance
5 | Purchasing | Find other than Approved PR From AutoCreate Option | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> AutoCreate 4) Approved Status as No and click find-> Take Screen shot 5) LogOut and Close the browser. | PO_FindOtherThanApprovedPRFromAutoCreateOption_00108 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-03-24 | Pass | Dev instance
6 | Purchasing | Error PopUP will encountered if PR is not approved PR | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> AutoCreate 4) Approved Status as No and click find-> select the PR -> Clcik Atuomtic-> Error Pop up will encounteted -> Click OK 5) LogOut and Close the browser. | PO_ErrorPopUP_On_StandarePOCreationFromWOApprovedPR_00109 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-03-25 | Pass | Dev instance
7 | Purchasing | Blanket Release Creation withOut Requisition | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> urchase_Order->Release 4) InPO Field, Search the PO details 5) Provide Line mumber, quantity, need By Date-> Save and capture the PO and Release number 6) Click the Approve Button-> OK 7) LogOut and Close the browser. | PO_BlanketReleaseCreation_WO_PR_00110(PO_BlanketReleaseCreation_WO_PR_00120) | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-03-26 | Pass | Dev instance
8 | Purchasing | Requisition creation in iProcurement(Using Search Option) | 1) Open the Browser 2) Login with correct user 3) CORP IPROCUREMENT ->iProcurement Home Page->Search field->Select one of the Items and Add to Cart 4)View Cart and Checkout->Update Deliver to Location->Apply->Next->Enter charge account and GL Date->Next->Submit 5)LogOut and Close the browser | PO_Requisition_Creation_In_iProcurement_00123 | 2020-03-29 | 2020-03-29 | 2020-03-29 | 2020-03-29 | Pass | Dev instance
9 | Purchasing | Requisition creation in iProcurement(Using Search Option) | 1) Open the Browser * 2) Login with correct user * 3) CORP IPROCUREMENT ->click the copy image 4)Checkout->provide GL Date->Next->Submit 5)LogOut and Close the browser | PO_Requisition_Creation_In_iProcurement_Using_CopyOption_00124 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | Pass | Dev instance
10 | Purchasing | Verify the quantity received and due eligibility | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> Purchase_Order->Purchase Summary 4) InPO Field, Search the PO details 5) Click Lines->Click Shipment button-> captured the quantity received and due 6) LogOut and Close the browser | PO_QtyReceived_QtyDue_EligibilityVerification_00112 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 2020-03-31 | Pass | Dev instance
11 | Purchasing | Receipt Shipment Mode Value needs to be required if Po returned to supplier | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> Receiving->Returns 4) Provide the PO number and Click on Find->Select the first row-> Provide the quantity and Supplier->Click Save 5) Error encountered, saying Receipt Transaction 6) LogOut and Close the browser | PO_ErrorPopUpOnReceiptTransactionBlankValue_00113 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-04-01 | Pass | Dev instance
12 | Purchasing | Return to supplier where Po number and line number is provided | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> Receiving->Returns 4) Provide the PO number and line number->Click on Find->Select the first row-> Provide the quantity and Supplier->Click Save 5) Error encountered, saying Receipt Transaction required-> provide the correct mode e:g- ship-> Click on Save 6) LogOut and Close the browser | PO_ReturnToSupplier_WithPO_LineNumber_00114 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2020-04-02 | Pass | Dev instance
13 | Purchasing | Return to supplier where Po number and line number is not provided, but it will take in alternative way | 1) Open the Browser 2) Login with correct user 3) Click on MWSPC_PURCHASING_SUPERUSE-> Receiving->Returns 4) do not Provide the PO number and line number->Simple Click on Find->Select the first row-> Provide the quantity and Supplier->Click Save 5) Error encountered, saying Receipt Transaction required-> provide the correct mode e:g- ship-> Click on Save 6) LogOut and Close the browser | PO_ReturnToSupplier_WO_PO_Number_Provided_00115 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-04-08 | Pass | Dev instance
14 | Purchasing | PO Receipt Creation | 1) Login the application 2)Navigate to MIMC_PURCHASING_BUYER->Receipts->Receipts 3)Provide Po number 4)Click Find button 5) Click Save and Click Header 6) Capture the receipt number 7)Log out from the application 8)Close the browser | PO_ReceiptCreation_00116 | 2020-04-09 | 2020-04-09 | 2020-04-09 | 2020-04-09 | Pass | Dev instance
15 | Purchasing | Global Blanket Agreement Creation and send it to the approver for approval | 1) Login the application 2)navigate to MWSPC_PURCHASING_SUPERUSE->Purchase_Order->Purchase_Orders-> 3)Provides all required inputs 4)Click Submit button to generate the PO 5)Clcik Approve button to send it to approver-> Now it will go to the approver 6)Log out from the application 7)Close the browser | PO_GlobalBlanketAgreementCreation_00117 | 2020-04-10 | 2020-04-10 | 2020-04-10 | 2020-04-10 | Pass | Dev instance
16 | Purchasing | Adding PO into invoice | 1) Open the Browser * 2) Login with correct user * 3) Click on Finance Tab * 4) Create Invoice with a PO->Go * 5) Enter PO number and Click Go 6) Select the Line -> Add to Invoice 7) LogOut and Close the browser | PO_iSupplier_PurchaseOrder_AddToInvoice_00118 | 2020-04-11 | 2020-04-11 | 2020-04-11 | 2020-04-11 | Pass | Dev instance
17 | Purchasing | Remove PO from invoice | 1) Open the Browser * 2) Login with correct user * 3) Click on Finance Tab * 4) Create Invoice with a PO->Go * 5) Enter PO number and Click Go 6) Select the Line -> Add to Invoice 7) Select the Line -> Remove from Invoice 8) LogOut and Close the browser | PO_iSupplier_PurchaseOrder_RemoveFromInvoice_00119 | 2020-04-12 | 2020-04-12 | 2020-04-12 | 2020-04-12 | Pass | Dev instance
18 | Purchasing | Create the invoice | 1) Open the Browser * 2) Login with correct user * 3) Click on Finance Tab * 4) Create Invoice with a PO->Go * 5) Enter PO number and Click Go 6) Select the Line -> Add to Invoice 7) provide inputs RemitToAddress,RemitToBankAccount,CustomerTaxPayerID,InvoiceNumber,Text,Quantity-> Click Next-> Submit 8) capture the invoice number 9)LogOut and Close the browser | PO_iSupplier_InvoiceCreation_00120 | 2020-04-15 | 2020-04-15 | 2020-04-15 | 2020-04-15 | Pass | Prerequities- Invoice number should be unique
19 | Purchasing | Create one duplicate invoice- Error encountered | 1) Open the Browser * 2) Login with correct user * 3) Click on Finance Tab * 4) Create Invoice with a PO->Go * 5) Enter PO number and Click Go 6) Select the Line -> Add to Invoice 7) provide inputs RemitToAddress,RemitToBankAccount,CustomerTaxPayerID,duplicate InvoiceNumber 8) capture the error 9)LogOut and Close the browser. | PO_iSupplier_ErrorOn_DuplicateInvoiceCreation_00121 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | Pass | Dev instance
20 | Purchasing | View/Search any Invoice details and get the PO number from it | 1) Open the Browser * 2) Login with correct user * 3) Click on Finance Tab * 4) Click View Invoice tab * 5) Provides invoice number and Click Go 6) capture the PO number 9)LogOut and Close the browser | PO_iSupplier_View_InvoiceDetails_00122 | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2020-04-17 | Pass | Dev instance