## Test Scenarios
Sl. No. | Application Name | Module | functional business process | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status
1 | EBS | iProcurement | Create Purchase Requisition | PR_RequisitionCreation_ORG_Unit_MWSPC_001 | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-10-01 | Pass
2 | EBS | iProcurement | Create Purchase Requisition without Charge Account(Negative scenario) | PR_RequisitionCreation_WO_ChargeAccount_N_002 | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-03 | Pass
3 | EBS | iProcurement | Create Purchase Requisition with Need-By-Date as past date(Negative scenario) | PR_RequisitionCreation_NeedByDateAsPast_N_003 | 2019-10-06 | 2019-10-06 | 2019-10-06 | 2019-10-06 | Pass
4 | EBS | iProcurement | Purchase Requisition Status Verification | PR_RequisitionStatusValidation_004 | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2019-10-09 | Pass
5 | EBS | iProcurement | Purchase Requisition Approval hierarchy | PR_ApprovedRequisitionHierarchy_005 | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2019-10-10 | Pass
6 | EBS | iProcurement | Create Purchase Requisition with Service type | PR_RequisitionCreation_TypeAsServiceUsingSearchOption_006 | 2019-10-13 | 2019-10-13 | 2019-10-13 | 2019-10-13 | Pass
7 | EBS | iProcurement | Create Purchase Requisition with mandatory field only | PR_RequisitionCreationMandatoryFieldOnly_007 | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-10-14 | Pass
8 | EBS | iProcurement | Search the Purchase Requisition in different Organization Unit(Negative scenario) | PR_RequisitionSearchInOther_ORG_Unit_008 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | Pass
9 | EBS | iProcurement | Blank Search- Multi status Purchase Requisition returned | PR_RequisitionBlankSearch_009 | 2019-10-16 | 2019-10-16 | 2019-10-16 | 2019-10-16 | Pass
10 | EBS | iProcurement | Purchase Requisition search with Approved status -Only approved PR populated | PR_RequisitionApprovedSearch_010 | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2019-10-17 | Pass
11 | EBS | iProcurement | Create and approve the requisition(Whole process) | PO_CreateRequisitionAndApproval_011 | 2019-09-17 | 2019-09-30 | 2019-09-30 | 2019-09-30 | Pass
12 | EBS | iProcurement | Purchase Requisition search with InProcess status - Only InProcess PR populated | PR_RequisitionInProcessSearch_001 | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2019-09-18 | Pass
13 | EBS | iProcurement | Purchase Requisition search with specific date range | PR_SpecificDateRangePeriod_RequisitionSearch_002 | 2019-09-19 | 2019-09-19 | 2019-09-19 | 2019-09-19 | Pass
14 | EBS | Purchasing | Buyer details validation from the purchase requisition | PR_BuyerVerificationOnRequisition_003 | 2019-09-22 | 2019-09-22 | 2019-09-22 | 2019-09-22 | Pass
15 | EBS | Purchasing | Assign buyer on In Process requisition | PR_AssignBuyerOnInProcessRequisition_004 | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-09-23 | Pass
16 | EBS | Purchasing | Assign buyer on Approved requisition | PR_AssignBuyerOnApprovedRequisition_005 | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2019-09-24 | Pass
17 | EBS | Purchasing | Change the Buyer on an Approved Requisition | PO_ChangeBuyerInRequisition_002 | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-09-25 | Pass
18 | EBS | iProcurement | Purchase Requisition search with Rejected status - Only Rejected PR populated | PR_RequisitionRejectedSearch_001 | 2019-10-20 | 2019-10-20 | 2019-10-20 | 2019-10-20 | Pass
19 | EBS | iProcurement | Approver needs more information from the PR Creator | PR_ApproverNeedMoreInfo_002 | 2019-10-21 | 2019-10-21 | 2019-10-21 | 2019-10-21 | Pass
20 | EBS | iProcurement | Approver needs more information from the PR Creator without providing "Information Requested" | PR_ApproverSubmitRequestWithoutInformationToPRCreator_006 | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2019-10-22 | Pass
21 | EBS | iProcurement | Approver needs more information from the PR Creator while assign it to other user | PR_ApproverSubmitRequestWithoutInformationToOtherUser_N_007 | 2019-10-23 | 2019-10-23 | 2019-10-23 | 2019-10-23 | Pass
22 | EBS | iProcurement | Application Navigational flow check- Return to Worklist after open the PR record | PR_ReturnToWorklist_008 | 2019-10-24 | 2019-10-24 | 2019-10-24 | 2019-10-24 | Pass
23 | EBS | iProcurement | Approver needs more information from other user but did not provide the user details(Negative Scenario) | PR_AlertPopUPOnLogout_009 | 2019-10-27 | 2019-10-27 | 2019-10-27 | 2019-10-27 | Pass
24 | EBS | iProcurement | Approver Need more information from other user by EmployeeName | PR_NeedMoreInfo_OU_EMPName_010 | 2019-10-28 | 2019-10-28 | 2019-10-28 | 2019-10-28 | Pass
25 | EBS | iProcurement | Application Navigational flow check- User Return back to "Home" page from worklist requisition page | PR_ReturnToHomePage_011 | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2019-10-29 | Pass
26 | EBS | iProcurement | Application Navigational flow check- "Oracle Applications Home Page" hyperlink should work | PR_OracleApplicationsHome PageHypLink_012 | 2019-10-30 | 2019-10-30 | 2019-10-30 | 2019-10-30 | Pass
27 | EBS | iProcurement | Approver Reject the Requsition | PR_ApproverRejectedRequsition_013 | 2019-10-31 | 2019-10-31 | 2019-10-31 | 2019-10-31 | Pass
28 | EBS | iProcurement | Rejected Purchase Requisition - Creator verify the rejected requisition | PR_ValidateRejectionRequsitionAtCreatorEnd_014 | 2019-11-03 | 2019-11-03 | 2019-11-03 | 2019-11-03 | Pass
29 | EBS | iProcurement | Rejected Purchase Requisition - Without Edit the cart and save the changes. | PR_SaveRejectedRequisitionWOEditCartFromResubmitLink_0015 | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2019-11-04 | Pass
30 | EBS | iProcurement | Rejected Purchase Requisition - Edit the cart and save the changes. Open the rejected requisition click on re-submit link Change the cart and save it | PR_SaveRejectedRequisitionWithEditCartFromResubmitLink_0016 | 2019-11-05 | 2019-11-05 | 2019-11-05 | 2019-11-05 | Pass
31 | EBS | iProcurement | Rejected Purchase Requisition - checkout without edit the shopping cart | PR_CheckoutRejectedPR_WOEditShoppingCart_0017 | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2019-11-06 | Pass
32 | EBS | iProcurement | Validate the resubmit PR from user at Approver end | PR_ValidateReSubmitRejectedPRAvibilityAtAproverEnd_018 | 2019-11-07 | 2019-11-07 | 2019-11-07 | 2019-11-07 | Pass
33 | EBS | iProcurement | Edit the PR with charge code as < 100 % and check out the process | PR_EditPR_ChrgAccountBelow100Pcntage_019 | 2019-11-10 | 2019-11-10 | 2019-11-10 | 2019-11-10 | Pass
34 | EBS | iProcurement | Edit the PR with charge code as > 100 % and check out the process | PR_EditPR_ChrgAccountAbove100Pcntage_020 | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-11-11 | Pass
35 | EBS | iProcurement | Delete only charge code from the more information required PR(Negative Scenario) | PR_DeleteChargeAccount_FromEditPR_021 | 2019-11-12 | 2019-11-12 | 2019-11-12 | 2019-11-12 | Pass
36 | EBS | iProcurement | Application Navigational flow check- Close Approver cart and return back to edit requisition page | PR_CloseApproverCart_FromEditPR_022 | 2019-11-13 | 2019-11-13 | 2019-11-13 | 2019-11-13 | Pass
37 | EBS | iProcurement | Split cost on Purchase Requisition | PR_SplitCostAllocationValidationOnPR_023 | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2019-11-14 | Pass
38 | EBS | iProcurement | Purchase Requisition search with PreApproved Status | PR_RequisitionInPreApprovedSearch_0024 | 2019-11-18 | 2019-11-18 | 2019-11-18 | 2019-11-18 | Pass
39 | EBS | iProcurement | Purchase Requisition search with Returned status | PR_RequisitionReturnedSearch_0025 | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-11-19 | Pass
40 | EBS | iProcurement | Verify the charge account fund details on edit PR | PR_ChkFund_ChrgAcct_MoreInfoPR_0026 | 2019-11-20 | 2019-11-20 | 2019-11-20 | 2019-11-20 | Pass
41 | EBS | iProcurement | Add multiple charge account on a PR | PR_Add_Unique_Multi_ChrgAcct_AddOnMoreInfoPR_0027 | 2019-11-21 | 2019-11-21 | 2019-11-21 | 2019-11-21 | Pass
42 | EBS | iProcurement | Add duplicate charge account on edit PR | PR_Add_Duplicate_Multi_ChrgAcct_OnMoreInfoPR_0028 | 2019-11-24 | 2019-11-24 | 2019-11-24 | 2019-11-24 | Pass
43 | EBS | iProcurement | Change the GLDate from date on edit PR | PR_GLDateChangesToMultiple_0029 | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2019-11-25 | Pass
44 | EBS | iProcurement | Shopping Cart link navigation flow validation | PR_ShoppingCartLinkValidation_0030 | 2019-11-26 | 2019-11-26 | 2019-11-26 | 2019-11-26 | Pass
45 | EBS | iProcurement | Resubmit the PR with "Deliver-To Location" as "Location" | PR_EditPR_EditLine_DeliverToLocation_ByLocation_0031 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | Pass
46 | EBS | iProcurement | Resubmit the PR with "Deliver-To Location" as "Organization" | PR_EditPR_EditLineDeliverToLocationByOrganization_0032 | 2019-11-28 | 2019-11-28 | 2019-11-28 | 2019-11-28 | Pass
47 | EBS | iProcurement | Resubmit the PR with Need By Date as past date (Negative Scenario) | PR_EditPR_AsPastNeedByDate_0033 | 2019-12-01 | 2019-12-01 | 2019-12-01 | 2019-12-01 | Pass
48 | EBS | iProcurement | Resubmit the PR - Choose Approver name using By name | PR_ManageApprovals_InsertApprovarByName_0034 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-02 | Pass
49 | EBS | iProcurement | Resubmit the PR - Choose duplicate Approver name | PR_ManageApprovals_InsertduplicateApprovarByName_0035 | 2019-12-03 | 2019-12-03 | 2019-12-03 | 2019-12-03 | Pass
50 | EBS | iProcurement | Delete the Approver name from the PR | PR_ManageApprovals_DeleteApprover_0036 | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2019-12-04 | Pass
51 | EBS | iProcurement | Resubmit the PR - Choose Approver name using By Email Id | PR_ManageApprovals_InsertApprovarByEmail_0037 | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2019-12-05 | Pass
52 | EBS | iProcurement | Delete the Item from shopping cart | PR_DeleteItemFRMApproverShoppingCart_0038 | 2019-12-08 | 2019-12-08 | 2019-12-08 | 2019-12-08 | Pass
53 | EBS | iProcurement | Application Navigation flow - "PR Details" hyperlink should work | PR_OpePRDetailsLinkValidation_0039 | 2019-12-09 | 2019-12-09 | 2019-12-09 | 2019-12-09 | Pass
54 | EBS | iProcurement | Copy the requisition to the existing requisition( "Copy To Cart") | PR_Requisition_CopyToCart_AddToCart_0040 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | Pass
55 | EBS | iProcurement | Copy the requisition to the existing requisition ("New To Cart") | PR_Requisition_CopyToCart_NewCart_0041 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | Pass
56 | EBS | iProcurement | Purchase Requisition search within 7days | PR_Search7daysCreatedRequisition_0042 | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-12 | Pass
57 | EBS | iProcurement | Home page title of Oracle Applications validation | PR_VerifyHomePageTitle_0043 | 2019-12-16 | 2019-12-16 | 2019-12-16 | 2019-12-16 | Pass
58 | EBS | iProcurement | Purchase Requisition search - last 30 days | PR_SearchLast30DaysCreatedRequisition_0044 | 2019-12-18 | 2019-12-18 | 2019-12-18 | 2019-12-18 | Pass
59 | EBS | iProcurement | Purchase Requisition search - last 60 days | PR_SearchLast60DaysCreatedRequisition_0045 | 2019-12-19 | 2019-12-19 | 2019-12-19 | 2019-12-19 | Pass
60 | EBS | iProcurement | Cancelled Purchase Requisition search - last 60 days | PR_SearchCancelledRequisitionOnlyInLast60Days_0046 | 2019-12-22 | 2019-12-22 | 2019-12-22 | 2019-12-22 | Pass
61 | EBS | iProcurement | Rejected Purchase Requisition search - Any Time | PR_SearchRejectedRequisitionOnlyAtAnyTimesAsCreationDate_0047 | 2019-12-23 | 2019-12-23 | 2019-12-23 | 2019-12-23 | Pass
62 | EBS | iProcurement | Search Inprocess PRs and add item to cart using "Coy to Cart" option then delete it from the cart | PR_SearchInProcessPR_CopyToCart_AddTocart_DeleteFrmCart_0048 | 2019-12-24 | 2019-12-24 | 2019-12-24 | 2019-12-24 | Pass
63 | EBS | iProcurement | Search Cancelled PRs and add item to cart using "Copy to Cart" option then delete it from the cart | PR_SearchCancelledPR_CopyToCart_AddTocart_DeleteFrmCart_0049 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | Pass
64 | EBS | iProcurement | Cancell the already cancelled Purchase Requisition(Negative scenario) | PR_CancelRequisitionOnCanceledPR_N_0050 | 2019-12-26 | 2019-12-26 | 2019-12-26 | 2019-12-26 | Pass
65 | EBS | iProcurement | Change the cancelled Purchase Requisition(Negative scenario) | PR_Change_CancelledRequisition_N_0051 | 2019-12-29 | 2019-12-29 | 2019-12-29 | 2019-12-29 | Pass
66 | EBS | iProcurement | Error message validation - if you will perform any action without selecting any PR (negative scenario) | PR_ValidateErrorMSGIfPRnotSelectedAndtryingToDoActionAnything_N_0052 | 2019-12-30 | 2019-12-30 | 2019-12-30 | 2019-12-30 | Pass
67 | EBS | iProcurement | Validate the Oracle iProcurement: Checkout page title | PR_VerifyiProcurementPageTitle_0053 | 2019-12-31 | 2019-12-31 | 2019-12-31 | 2019-12-31 | Pass
68 | EBS | iProcurement | Validate the landing page title "Notification Details" on created PR | PR_VerifyNotificationLandingPageTitle_0054 | 2020-01-01 | 2020-01-01 | 2020-01-01 | 2020-01-01 | Pass
69 | EBS | iProcurement | Partially cancel the PR | PR_PartiallyCancelPR_0055 | 2020-01-02 | 2020-01-02 | 2020-01-02 | 2020-01-02 | Pass
70 | EBS | iProcurement | Cancel the entire PR | PR_CancelEntirePR_0056 | 2020-01-05 | 2020-01-05 | 2020-01-05 | 2020-01-06 | Pass
71 | EBS | iProcurement | Application Navigation Flow- Cancel button | PR_CancelTransactionAndReturnBackToOriginalSearch_0057 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 2020-01-07 | Pass
72 | EBS | iProcurement | Cancel Page title validation | PR_CancelPageTitleVerification_0058 | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-08 | Pass
73 | EBS | iProcurement | Complete the requisitions from Inprocess data | PR_CompleteRequisitionsInprocessData_0059 | 2020-01-08 | 2020-01-08 | 2020-01-08 | 2020-01-09 | Pass
74 | EBS | iProcurement | Search Incomplete PR from Edit PR page | PR_SearchAnyTimeIncompleteStatusesPR_0060 | 2020-01-09 | 2020-01-09 | 2020-01-09 | 2020-01-10 | Pass
75 | EBS | iProcurement | Complete the Incomplete requisition | PR_CompleteTheIncompletePR_0061 | 2020-01-12 | 2020-01-12 | 2020-01-12 | 2020-01-13 | Pass
76 | EBS | iProcurement | Valida the status from "Incompelete" to "Inprocess" | PR_Verify_Inproces_As_Status_AfterChanged_FRM_IncompeletePR_0062 | 2020-01-13 | 2020-01-13 | 2020-01-13 | 2020-01-14 | Pass
77 | EBS | iProcurement | Clear Button Functionlity check | PR_ClearButtonTestFunctionlity_0063 | 2020-01-14 | 2020-01-14 | 2020-01-14 | 2020-01-16 | Pass
78 | EBS | iProcurement | Validate the Requisition Notification PageTitle | PR_Validate_Requisition_Notification_PageTitle_0064 | 2020-01-19 | 2020-01-19 | 2020-01-19 | 2020-01-19 | Pass
79 | EBS | iProcurement | Purchase Requisition Notification - "Select All" link should select all the records | PR_Requisition_Notification_SelectAllCheckBoxUsing_SelectAll_Link_0065 | 2020-01-20 | 2020-01-20 | 2020-01-20 | 2020-01-20 | Pass
80 | EBS | iProcurement | Purchase Requisition Notification - "Select none" link should de-select all the selected records | PR_Requisition_Notification_SelectNoneCheckBoxsUsing_Selectnone_Link_0066 | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-01-21 | Pass
81 | EBS | iProcurement | Purchase Requisition Notification - Open the notification using notification link(validate the text after opned it) | PR_Requisition_Notification_openNotificationUsingNotificationLink_0067 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | Pass
82 | EBS | iProcurement | Purchase Requisition Notification - Open the notification using Open button(validate the text after opned it) | PR_Requisition_Notification_openNotificationUsing_OpenButton_0068 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 2020-01-23 | Pass
83 | EBS | iProcurement | Purchase Requisition Notification - Error message validation, if open button click without selecting any notification | PR_Requisition_Notification_ClickOpenButtonWithoutSelectingCheckBox_N_0069 | 2020-01-25 | 2020-01-25 | 2020-01-25 | 2020-01-25 | Pass
84 | EBS | iProcurement | Purchase Requisition Notification - Error message validation, if Reassign without selecting any notification | PR_Requisition_Notification_ClickReassignButtonWithoutSelectingAnyCheckBox_N_0070 | 2020-01-26 | 2020-01-26 | 2020-01-26 | 2020-01-26 | Pass
85 | EBS | iProcurement | Purchase Requisition Notification - Error message validation, if Reassign After selecting any notification | PR_Requisition_Notification_ClickReassignButtonAfterSelectNotificationCheckBox_N_0071 | 2020-01-27 | 2020-01-27 | 2020-01-27 | 2020-01-27 | Pass
86 | EBS | iProcurement | Purchase Requisition Notification - Error message validation, if you click Close button without selecting any notification | PR_Requisition_Notification_ClickCloseButtonWOSelectAnyNotificationCheckBox_N_0072 | 2020-01-28 | 2020-01-28 | 2020-01-28 | 2020-01-28 | Pass
87 | EBS | iProcurement | Purchase Requisition Notification - Error message validation, Select any notification and click close button | PR_Requisition_Notification_SelectAnyNotificationAndClickCloseButton_N_0073 | 2020-01-29 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Pass
88 | EBS | iProcurement | Purchase Requisition Notification - All Opened Notification opened by default, while opening the notification page | PR_Requisition_Notification_OpenNotificationByDefaultSelectedValidation_N_0074 | 2020-02-01 | 2020-02-01 | 2020-02-01 | 2020-02-01 | Pass
89 | EBS | iProcurement | Open All Notification list from notification page using notification dropdown | PR_Requisition_Notification_SelectAllNotificationFromDropDownList_0075 | 2020-02-02 | 2020-02-02 | 2020-02-02 | 2020-02-02 | Pass
90 | EBS | iProcurement | Requisition Approvals page - Open with "Requisitions to Approve" option | PR_Requisition_Approvals_RequisitionsToApproveByDefaultSelectedValidation_0076 | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-02-03 | Pass
91 | EBS | iProcurement | Open the "Requisitions I Have Approved" details from Requisition->Approvals tab | PR_Requisition_Approvals_Validate_Requisitions_I_Have_Approved_Option_0077 | 2020-02-04 | 2020-02-04 | 2020-02-04 | 2020-02-04 | Pass
92 | EBS | iProcurement | Verify the iProcurement Shop page Title | PR_iProcurement_Shop_Title_Verification_0078 | 2020-02-05 | 2020-02-05 | 2020-02-05 | 2020-02-05 | Pass
93 | EBS | iProcurement | Verify the iProcurement receiving page Title | PR_iProcurement_Receiving_Title_Verification_0079 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | Pass
94 | EBS | iProcurement | Validate the store landing page after clicking store link from Shop Tab. | PR_iProcurement_Shop_StorePage_Verification_0080 | 2020-02-09 | 2020-02-09 | 2020-02-09 | 2020-02-09 | Pass
95 | EBS | iProcurement | Validate the store landing page after clicking "Shopping List" link. | PR_iProcurement_Shop_ShoppingList_Verification_0081 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-02-10 | Pass
96 | EBS | iProcurement | Receiving landing page validation. | PR_iProcurement_Receiving_LandingPage_Verification_0082 | 2020-02-11 | 2020-02-11 | 2020-02-11 | 2020-02-11 | Pass
97 | EBS | iProcurement | Work Confirmations landing page validation. | PR_iProcurement_Receiving_workConfirmationPage_Verification_0083 | 2020-02-12 | 2020-02-12 | 2020-02-12 | 2020-02-12 | Pass
98 | EBS | Purchasing | Purchase Order Creation | PO_BlanketCreationWOApproval_0084 | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-02-18 | Pass
99 | EBS | Purchasing | Purchase Order Creation and send it for approval | PO_BlanketCreationAndSentToApproverForApproval_0085 | 2020-02-19 | 2020-02-19 | 2020-02-19 | 2020-02-19 | Pass
100 | EBS | Purchasing | Purchase Order Approval hierarchy | PO_BlanketCreationAndVerifyApproverDetails_0086 | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-20 | Pass
101 | EBS | Purchasing | Status and approver details for a given Purchase Order | PO_FindOutPOStatusOfGivenPO_0087 | 2020-02-23 | 2020-02-23 | 2020-02-23 | 2020-02-23 | Pass
102 | EBS | Purchasing | Blank Search- Multi status Purchase Oder returned | PO_Search_BlankPOSearch_0088 | 2020-02-24 | 2020-02-24 | 2020-02-24 | 2020-02-24 | Pass
103 | EBS | Purchasing | Purchase Order search with Approved status -Only approved PO populated | PO_Search_ApprovedPOSearch_0089 | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-02-25 | Pass
104 | EBS | Purchasing | Purchase Requisition search with InProcess status -Only Inprocessed PO populated | PO_Search_InProcessPOSearch_0090 | 2020-02-26 | 2020-02-26 | 2020-02-26 | 2020-02-26 | Pass
105 | EBS | Purchasing | Retrive a list of Purchase Order withing specific date | PO_Search_SpecificDateRange_0091 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 | Pass
106 | EBS | Purchasing | Error message - if the search date is mis-matched. | PO_Search_ErrorMSGValidationOnDateRangeMismatch_0092 | 2020-03-01 | 2020-03-01 | 2020-03-01 | 2020-03-01 | Pass
107 | EBS | Purchasing | Error message - if search criteria fail w.r.t PO status(e.g- Approved, In Process etc.) | PO_Search_ErrorMSGValidationIfStatusPONotFound_0093 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 2020-03-02 | Pass
108 | EBS | Purchasing | Purchase Order search - Approved in status and specfic date range | PO_Search_ApprovedStatusPOWithinSpecificDateRange_0094 | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-03-03 | Pass
109 | EBS | Purchasing | Purchase Order search - In process in status and specfic date range | PO_Search_InProcessPOStatusWithinSpecificDateRange_0095 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-03-04 | Pass
110 | EBS | Purchasing | Search Purchase Order using the contract id | PO_Search_UsingContractID_0096 | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-03-05 | Pass
111 | EBS | Purchasing | Get the Purchase Order details using Line SupplierItemID | PO_Search_FindPODetails_UsingLine_SupplierItemID_0097 | 2020-03-08 | 2020-03-08 | 2020-03-08 | 2020-03-08 | Pass
112 | EBS | Purchasing | Get the Purchase Order details using Line LocationId | PO_Search_FindPODetails_UsingLocationId_0098 | 2020-03-09 | 2020-03-09 | 2020-03-09 | 2020-03-09 | Pass
113 | EBS | Purchasing | Get the Purchase Order details using Line Account Period dates | PO_Search_FindPODetails_UsingSpecificAccountingDates_0099 | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 | Pass
114 | EBS | Purchasing | Get the Purchase Order details using ChargeCode | PO_Search_FindPODetails_UsingChargeCode_00100 | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-03-11 | Pass
115 | EBS | Purchasing | Get the Purchase Order details using Line-> Account Period dates along with Charge code(combination of accounts dates and charge code) | PO_Search_FindPODetails_WithinDateRangeWithChargeCode_00101 | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-03-12 | Pass
116 | EBS | Purchasing | Get the Purchase Order details using Invoice Number | PO_Search_FindPODetailsUsing_Invoice_Number_00102 | 2020-03-15 | 2020-03-15 | 2020-03-15 | 2020-03-15 | Pass
117 | EBS | Purchasing | Get the Purchase Order details using Receipt Number | PO_Search_FindPODetailsUsing_Receipt_Number_00103 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 2020-03-16 | Pass
118 | EBS | Purchasing | Standard Purchase Order creation from PR | PO_StandarePOCreationFromPR_00104 | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2020-03-18 | Pass
119 | EBS | Purchasing | Standared Purchase Order Creation Without PR | PO_StandarePOCreation_WO_PR_00105 | 2020-03-19 | 2020-03-19 | 2020-03-19 | 2020-03-19 | Pass
120 | EBS | Purchasing | Purchase Order Creation- Error PopUp encountered while provide incorrect PromiseDate | PO_ErroValidationOnIncorrectPromiseDate_00106 | 2020-03-22 | 2020-03-22 | 2020-03-22 | 2020-03-22 | Pass
121 | EBS | iProcurement | Find Approved PR From AutoCreate Option | PO_FindApprovedPRFromAutoCreateOption_00107 | 2020-03-23 | 2020-03-23 | 2020-03-23 | 2020-03-23 | Pass
122 | EBS | iProcurement | Find other than Approved PR From AutoCreate Option | PO_FindOtherThanApprovedPRFromAutoCreateOption_00108 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-03-24 | Pass
123 | EBS | Purchasing | Error PopUP will encountered if PR is not approved PR | PO_ErrorPopUP_On_StandarePOCreationFromWOApprovedPR_00109 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-03-25 | Pass
124 | EBS | Purchasing | Blanket Release Creation withOut Requisition | PO_BlanketReleaseCreation_WO_PR_00110(PO_BlanketReleaseCreation_WO_PR_00120) | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-03-26 | Pass
125 | EBS | iProcurement | Requisition creation in iProcurement(Using Search Option) | PO_Requisition_Creation_In_iProcurement_00123 | 2020-03-29 | 2020-03-29 | 2020-03-29 | 2020-03-29 | Pass
126 | EBS | iProcurement | Requisition creation in iProcurement(Using Copy Option) | PO_Requisition_Creation_In_iProcurement_Using_CopyOption_00124 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | Pass
127 | EBS | iProcurement | Verify the quantity received and due eligibility | PO_QtyReceived_QtyDue_EligibilityVerification_00112 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 2020-03-31 | Pass
128 | EBS | Purchasing / iProcurement | Return to Supplier - Purchase Order returned to supplier without Receipt Shipment Mode (negative scenario) | PO_ErrorPopUpOnReceiptTransactionBlankValue_00113 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-04-01 | Pass
129 | EBS | Purchasing / iProcurement | Return to supplier - where Purchase Order number and line number is provided | PO_ReturnToSupplier_WithPO_LineNumber_00114 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2020-04-02 | Pass
130 | EBS | Purchasing / iProcurement | Return to supplier - where Purchase Order number and line number is not provided | PO_ReturnToSupplier_WO_PO_Number_Provided_00115 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-04-08 | Pass
131 | EBS | Purchasing / iProcurement | PO Receipt Creation | PO_ReceiptCreation_00116 | 2020-04-09 | 2020-04-09 | 2020-04-09 | 2020-04-09 | Pass
132 | EBS | Purchasing | Global Blanket Agreement Creation and send it to the approver for approval | PO_GlobalBlanketAgreementCreation_00117 | 2020-04-10 | 2020-04-10 | 2020-04-10 | 2020-04-10 | Pass
133 | EBS | iSupplier | Adding PO into invoice | PO_iSupplier_PurchaseOrder_AddToInvoice_00118 | 2020-04-11 | 2020-04-11 | 2020-04-11 | 2020-04-11 | Pass
134 | EBS | iSupplier | Remove PO from invoice | PO_iSupplier_PurchaseOrder_RemoveFromInvoice_00119 | 2020-04-12 | 2020-04-12 | 2020-04-12 | 2020-04-12 | Pass
135 | EBS | iSupplier | Create the invoice | PO_iSupplier_InvoiceCreation_00120 | 2020-04-15 | 2020-04-15 | 2020-04-15 | 2020-04-15 | Pass
136 | EBS | iSupplier | Create one duplicate invoice- Error encountered | PO_iSupplier_ErrorOn_DuplicateInvoiceCreation_00121 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | Pass
137 | EBS | iSupplier | Get Purchase Order number on any Invoice | PO_iSupplier_View_InvoiceDetails_00122 | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2020-04-17 | Pass

## Sheet1
Enter & Process Purchase Requisitions for Inventory Items
Enter & Process Purchase Requisitions for Expense Items
Enter & Process Purchase Requisitions Without Suppliers
Amend Incomplete, Approved & In Process PRs
Standard Purchase Order creation using Expense based PR
Standard Purchase Order creation using Inv. Item based PR
Direct Standard Purchase Order creation
Blanket Release using Autocreate
Global Blanket Purchase Agreement Creation
Blanket Release without PR (Direct)
PO Receiving and Deliver to Subinventory
Enter & Process Purchase Requistion from iProcurement
Receive in iProcurement
Return To Vendor
Create an RFQ – Autocreation from Requisition
Enter and Process Quotations
PO Maintenance
PO Control
Req creation à Req Approval
Blanket Release creation from PR
Standard PO creation from PR
PO Receipt creation
Invoice creation
Assign a Buyer to an Approved Requisition where the Buyer is unavailable
Change the Buyer on an Approved Requisition
Return to Supplier
Global Blanket Agreement Creation
Blanket Release creation without a Purchase Requisition
Standard PO creation without a PR
Update a PO while In Process status
PO Receiving and Deliver to Sub Inventory
Requisition creation in iProcurement
Receive in iProcurement
PO Corrections
Creation of Two Stage RFQ- Approval
Publish RFQ
Quotation by Suppliers
Close RFQ
Unlock Technical
Enter Technical Score
Unseal Stage: Technical
Lock Scoring and Complete Technical Evaluation
Unlock Stage: Commercial
Enter Commercial Score
Unseal Stage: Commercial and Lock Scoring
Award by Quote
Express Receive – iProcurement
Reject a Purchase Order, Update and Submit for Approval
Internal Requisition