## Sprint1
Sl. No. | Module | Scenarios | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | PO | Req creation in (Form) and Approval | 2019-08-11 | 2019-08-11 | 2019-08-11 | 2019-08-11 | Done
2 | PO | Change the Buyer in a Requisition when it's In Process / Approved status | 2019-08-12 | 2019-08-12 |  |  | Pending | Not yet executed
3 | PO | Standard PO creation from PR and PO Approval | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-08-13 | Done
4 | PO | Standard PO creation without a PR and PO Approval | 2019-08-14 | 2019-08-14 | 2019-08-20 | 2019-08-20 | Done
5 | PO | Blanket Agreement creation and Approval | 2019-08-15 | 2019-08-15 | 2019-08-15 | 2019-08-15 | Done
6 | PO | Blanket Release creation from PR and Approval | 2019-08-18 | 2019-08-18 | 2019-08-18 | 2019-08-18 | Done | After Click Auto create, requestion number(approved-711802628) created from USER- MECEVICM is not fount, however while trying to create the autocreate using MECEVICM user, it encountered error- Byer not set
7 | PO | Blanket Release creation without a PR and Approval | 2019-08-19 | 2019-08-19 | 2019-08-20 | 2019-08-20 | Done
8 | PO | Update a PO to upload attachments while the PO is In Process status | 2019-08-20 | 2019-08-20 |  |  | Pending | Not yet executed
9 | PO | Receipt creation with Direct delivery to Sub inventory | 2019-08-21 | 2019-08-21 |  |  | Pending | Not yet executed
10 | PO | Receiving and then Deliver | 2019-08-22 | 2019-08-22 |  |  | Pending | Not yet executed
11 | PO | Express Receipt | 2019-08-25 | 2019-08-25 |  |  | Pending | Not yet executed
12 | PO | Requisition creation in iProcurement and Approval | 2019-08-26 | 2019-08-26 |  |  | Pending | Not yet executed
13 | PO | Reject a Purchase Requisition / Purchase Order Update and Submit for Approval | 2019-08-27 | 2019-08-27 |  |  | Pending | Not yet executed
14 | PO | Internal Requisition | 2019-08-28 | 2019-08-28 |  |  | Pending | Not yet executed
15 | PO | Return to Supplier | 2019-08-29 | 2019-08-29 |  |  | Pending | Not yet executed
16 | PO | RFQ Creation - Approval | 2019-09-01 | 2019-09-01 |  |  | Pending | Not yet executed
17 | PO | Two Stage RFQ creation | 2019-09-02 | 2019-09-02 |  |  | Pending | Not yet executed
18 | PO | Quotation by Suppliers | 2019-09-03 | 2019-09-03 |  |  | Pending | Not yet executed
19 | PO | Quotation Evaluation | 2019-09-04 | 2019-09-04 |  |  | Pending | Not yet executed
20 | PO | Award by Quote | 2019-09-05 | 2019-09-05 |  |  | Pending | Not yet executed