## Sprint1
Sl. No. | Module | Scenarios | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | Purchasing | Req creation in (Form) and Approval | 2019-08-11 | 2019-08-11 | 2019-08-11 | 2019-08-11 | Done
2 | Purchasing | Change the Buyer in a Requisition when it's In Process / Approved status | 2019-08-12 | 2019-08-12 | 2019-08-21 | 2019-08-21 | Done
3 | Purchasing | Standard PO creation from PR and PO Approval | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-08-13 | Done
4 | Purchasing | Standard PO creation without a PR and PO Approval | 2019-08-14 | 2019-08-14 | 2019-08-20 | 2019-08-20 | Done
5 | Purchasing | Blanket Agreement creation and Approval | 2019-08-15 | 2019-08-15 | 2019-08-15 | 2019-08-15 | Done
6 | Purchasing | Blanket Release creation from PR and Approval | 2019-08-18 | 2019-08-18 | 2019-08-18 | 2019-08-18 | Done | After Click Auto create, requestion number(approved-711802628) created from USER- MECEVICM is not fount, however while trying to create the autocreate using MECEVICM user, it encountered error- Byer not set
7 | Purchasing | Blanket Release creation without a PR and Approval | 2019-08-19 | 2019-08-19 | 2019-08-20 | 2019-08-20 | Done
8 | Purchasing | Update a PO to upload attachments while the PO is In Process status | 2019-08-20 | 2019-08-20 |  |  | Pending | Not yet executed
9 | Inventory | Receipt creation with Direct delivery to Sub inventory | 2019-08-21 | 2019-08-21 | 2019-08-22 | 2019-08-22 | Done
10 | Purchasing/ Inventory | Receiving and then Deliver | 2019-08-22 | 2019-08-22 |  |  | Pending | Not yet executed
11 | Purchasing/ Inventory | Express Receipt | 2019-08-25 | 2019-08-25 |  |  | Pending | Not yet executed
12 | iProcurement | Requisition creation in iProcurement and Approval | 2019-08-26 | 2019-08-26 |  |  | Pending | Not yet executed
13 | Purchasing | Reject a Purchase Requisition / Purchase Order Update and Submit for Approval | 2019-08-27 | 2019-08-27 |  |  | Pending | Not yet executed
14 | Purchasing | Internal Requisition | 2019-08-28 | 2019-08-28 |  |  | Pending | Not yet executed
15 | Purchasing | Return to Supplier | 2019-08-29 | 2019-08-29 |  |  | Pending | Not yet executed
16 | Sourcing | RFQ Creation - Approval | 2019-09-01 | 2019-09-01 |  |  | Pending | Not yet executed
17 | Sourcing | Two Stage RFQ creation | 2019-09-02 | 2019-09-02 |  |  | Pending | Not yet executed
18 | Sourcing | Quotation by Suppliers | 2019-09-03 | 2019-09-03 |  |  | Pending | Not yet executed
19 | Sourcing | Quotation Evaluation | 2019-09-04 | 2019-09-04 |  |  | Pending | Not yet executed
20 | Sourcing | Award by Quote | 2019-09-05 | 2019-09-05 |  |  | Pending | Not yet executed
HRMS

## Sheet1
Sl. No. | Module | Scenarios | Test Case Name | Plan Start Date | Plan End Date | Actual Start Date | Actual Closure Date | Status | Updates/Comments
1 | Purchasing | Purchase Requisition Creation under Purchasing Preparer Organization Unit as (MWSPC_PURCHASING_PREPARER) for single user(e:g - BRAHMEG) | PR_RequisitionCreation_ORG_Unit_MWSPC_001 | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-10-01 | Pass
2 | Purchasing | Purchase Requisition Creation without entering Charge Account details | PR_RequisitionCreation_WO_ChargeAccount_N_002 | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-03 | Pass
3 | Purchasing | Purchase Requisition Creation with Need-By-Date as past date | PR_RequisitionCreation_NeedByDateAsPast_N_003 | 2019-10-06 | 2019-10-06 | 2019-10-06 | 2019-10-06 | Pass
4 | Purchasing | Validate the status details of ctreated Reqution | PR_RequisitionStatusValidation_004 | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2019-10-09 | Pass
5 | Purchasing | Validate the hirchecy level details of a approved requestion | PR_ApprovedRequisitionHierarchy_005 | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2019-10-10 | Pass
6 | Purchasing | Create the Purchase Requisition with type as Service using search option | PR_RequisitionCreation_TypeAsServiceUsingSearchOption_006 | 2019-10-13 | 2019-10-13 | 2019-10-13 | 2019-10-13 | Pass
7 | Purchasing | Purchase Requisition Creation with mandatory field only | PR_RequisitionCreationMandatoryFieldOnly_007 | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-10-14 | Pass
8 | Purchasing | Search the requsition status in different Organization Unit (MPC PURCHASING BUYER) Requisition created on MWSPC_PURCHASING_PREPARER Try to find out in MPC PURCHASING BUYER | PR_RequisitionSearchInOther_ORG_Unit_008 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | Pass
9 | Purchasing | Return list of requisition number on Blank Search | PR_RequisitionBlankSearch_009 | 2019-10-16 | 2019-10-16 | 2019-10-16 | 2019-10-16 | Pass
10 | Purchasing | Return list of approved requisition number | PR_RequisitionApprovedSearch_010 | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2019-10-17 | Pass
11 | Purchasing | Create and approve the requisition(Whole process) | PO_CreateRequisitionAndApproval_011 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2019-09-30 | Pass
4 | PO | PO Receipt creation
Validate the Receipt Routing as Standard Receipt on PO
Assigning the Receipt Routing as Standard Receipt on PO
Validate the Buyer Details on Approved requsition
6 |  | Assign the Buyer if Buyer is unavailable on PO
|  | Global Blanket Agreement Creation |  | Link each other
Validate the status of the Global Blanket Agreement
Approval Process on Global Blanket Agreement