## Summary
System Test Script - Oracle HCM Cloud - Organization Development
Test Script Summary
Overview
Software / Release |  | HCM Cloud Release 13 |  |  | Note - The value entered propagates across all worksheets
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) |  |  | Note - The value entered propagates across all worksheets
Test Script Summary |  | Test Results
ID # | Test Script Name | Date Tested | Tested By | Test Status | Notes
Global HR - Admin Tests | [5 empty] | Automation Test Script | Comments
1.01 | Manage Locations |  |  |  |  | HCM_ManageLocations_EditLocation_0030 HCM_ManageLocations_CorrectionLocation_0031 HCM_ManageLocations_CreateLocation_0032
1.02 | Manage Divisions |  |  |  |  | HCM_ManageJobs_CreateNewDivision_0039 HCM_ManageJobs_CreateDivision_AnExistingOrganization_0040 HCM_ManageJobs_EditDivision_UpdateOption_0041 HCM_ManageJobs_EditDivision_CorrectOption_0042
1.03 | Manage Departments |  |  |  |  | HCM_ManageDepartments_CreateDepartment_0043 HCM_ManageDepartments_Create_ExistingDepartment_0044 HCM_ManageDepartments_EditDepartment_0045
1.04 | Manage Job Families |  |  |  |  | HCM_ManageJobFamilies_Create_JobFamilies_0033 HCM_ManageJobFamilies_Update_JobFamilies_0034 HCM_ManageJobFamilies_Correct_JobFamilies_0035
1.05 | Manage Job |  |  |  |  | HCM_ManageJobs_CreateJobs_WO_Grades_0036 HCM_ManageJobs_CreateJobs_CreateProfile_0037 HCM_ManageJobs_CreateJobs_AddExistingProfile_0038
1.06 | Manage Grades |  |  |  |  | HCM_Manage Grades_CreateGrade_0046 HCM_Manage Grades_CreatedulpicateGrades_0047 HCM_ManageGrades_EditGrades_0048 HCM_ManageGrades_Edit_CorrectGrades_0049
1.07 | Manage Grade Rates |  |  |  |  | HCM_ManageGradeRates_CreateGradeRates_0050 HCM_ManageGradeRates_CreateduplicateGradeRates_0051 HCM_ManageGradeRates_UpdateGradeRates_0052 HCM_ManageGradeRates_CorrectGradeRates_0053
1.08 | Manage Position |  |  |  |  | HCM_ManagePosition_CreatePosition_0054 HCM_ManagePosition_CreatePosition_With_ExistingProfile_0055 HCM_ManagePosition_UpdatePosition_0056 HCM_ManagePosition_CorrectPosition_0057
1.09 | Manage Organization Trees | [5 empty] | Data Not Available
1.1 | Generate Organization Hierarchy Report |  |  |  |  | HCM_GenerateOrganizationHierarchyReport_0058
1.11 | Generate Workforce Planning Report |  |  |  |  | HCM_GenerateWorkforcePlanningReport_0059
1.12 | Generate Manpower Budget Headcount Report | [5 empty] | Ravi Said not required as of now
1.13 | Generate Salary beyond the range report |  |  |  |  | HCM_GenerateSalaryBeyondtheRangeReport_0060
1.14 | Generate Missing Department Managers Report |  |  |  |  | HCM_GenerateMissingDepartmentManagersReport_0061
1.15 | Generate Missing Line Managers Report |  |  |  |  | HCM_GenerateMissingLineManagersReport_0062
1.16 | Generate Previous Experience Report | [5 empty] | Ravi Said not required as of now
1.17 | Generate Performance Rating Report | [5 empty] | Ravi Said not required as of now
1.18 | Generate Employee Attrition Report | [5 empty] | Ravi Said not required as of now
1.19 | Generate Manpower Report Monthly | [5 empty] | Ravi Said not required as of now
1.20 | Generate Annual Budget Report | [5 empty] | Ravi Said not required as of now
1.21 | Manage Costing of Departments |  |  |  |  | HCM_ManageCostingDepartments_0063 HCM_Edit_CostingDepartments_0064 HCM_Delete_CostingDepartments_0065 HCM_Correct_CostingDepartments_0066
1.22 | Generate Assignment History Report | [5 empty] | Ravi Said not required as of now
1.23 | Generate Salary History Report | [5 empty] | Ravi Said not required as of now
Ravi Said not required as of now

## 1.01
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Locations
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.01
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Locations through Implementation Project
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.01.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.01.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.01.003 | Navigation | Click on task name - 'Manage Locations' to navigate to task |  | The Implementation Project page appears
WS-1.01.004 | Search Location | To search for an existing Location, enter the name into the search box |  | Search successful
WS-1.01.005 | View Location | If there is a location that has the same name that was entered in the field, the data will be displayed under the Search Results |  | Results Display Successful
WS-1.01.006 | Edit Location | To update or correct the location, click Edit Icon |  | Edit Screen Appears
WS-1.01.007 | Edit Location | Select Effective Start Date, Click OK |  | Edit Screen Appears
WS-1.01.008 | Edit Location | Edit desired location information by selecting Edit |  | Edit Screen Appears
WS-1.01.009 | Save location edits | Click Submit |  | Submit window appears
WS-1.01.010 | Save location edits | Click Yes |  | Confirmation Window appears
WS-1.01.011 | Save location edits | Click OK |  | Save Successful
WS-1.01.012 | Save location edits | Click Done to return to overview page |  | Return Successful
WS-1.01.013 | Create new location | Click Create |  | Creation Screen Appears
WS-1.01.014 | Create new location | Enter the effective start date into the field |  | Entry Successful
WS-1.01.015 | Create new location | Select Location Set |  | Selection Successful
WS-1.01.016 | Create new location | Enter Location Name, Code and Description into fields | Enter Location Name, Code and Description into fields | Information Entry Successful
WS-1.01.017 | Create new location | Select a status |  | Status selection successful
WS-1.01.018 | Create new location | To select a country, select desired country from drop down menu |  | Desired country information displays
WS-1.01.019 | Create new location | Enter Address Information |  | Information Entry Successful
WS-1.01.020 | Create new location | Enter additional Information |  | Information Entry Successful
WS-1.01.021 | Save new Location | Click Submit |  | Submit window appears
WS-1.01.022 | Save new Location | Click Yes |  | Confirmation Window appears
WS-1.01.023 | Save new Location | Click OK |  | Save Successful
WS-1.01.024 | Save new Location | Click Done to return to overview page |  | Return Successful

## 1.02
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Divisions
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.02
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Divisions through Implementation Project
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.02.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.02.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.02.003 | Navigation | Click on task name - 'Manage Divisions' to navigate to task |  | The Implementation Project page appears
WS-1.02.004 | Search Division | To search for an existing Division, enter the name into the search box |  | Search successful
WS-1.02.005 | View Division | If there is a location that has the same name that was entered in the field, the data will be displayed under the Search Results |  | Results Display Successful
WS-1.02.006 | Edit Division | To update or correct the Division, click Edit Icon |  | Edit Screen Appears
WS-1.02.007 | Edit Division | Select Effective Start Date, Click OK |  | Edit Screen Appears
WS-1.02.008 | Edit Division | Edit Desired Division information |  | Information Entry Successful
WS-1.02.009 | Save Division Edits | Click Submit |  | Submit window appears
WS-1.02.010 | Save Division Edits | Click Yes |  | Confirmation Window appears
WS-1.02.011 | Save Division Edits | Click OK |  | Save Successful
WS-1.02.012 | Save Division Edits | Click Done to return to overview page |  | Return Successful
WS-1.02.013 | Create New Division | Click Create Icon |  | Creation Screen Appears
WS-1.02.014 | Create New Division | Select either create a new division or an existing organization to define as a division |  | Selection Successful
WS-1.02.015 | Create New Division | Enter effective start date |  | Entry Successful
WS-1.02.016 | Create New Division | Enter Division Name, Action Reason, and location | Enter Division Name, Action Reason, and location | Information Entry Successful
WS-1.02.017 | Create New Division | To view the Division Details page, click Next |  | Division Details Screen Appears
WS-1.02.018 | Create New Division | Enter a reporting name into the field |  | Information Entry Successful
WS-1.02.019 | Create New Division | Select Manager from Dropdown list |  | Selection Successful
WS-1.02.020 | Save New Division | Click Submit |  | Submit window appears
WS-1.02.021 | Save New Division | Click Yes |  | Confirmation Window appears
WS-1.02.022 | Save New Division | Click OK |  | Save Successful
WS-1.02.023 | Save New Division | Click Done to return to overview page |  | Return Successful

## 1.03
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Departments
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.03
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Departments through Implementation Project
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.03.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.03.002 | Navigation | Click on tasklist icon present on the right side of the application window. | Click Manage Implementation Projects | The Manage Implementation Projects page appears
WS-1.03.003 | Navigation | Click on task name - 'Manage Departments' to navigate to task |  | The Manage Departments page appears
WS-1.03.004 | Search Departments | Enter the appropriate information into at least one required fields, Click Search |  | Search successful
WS-1.03.005 | Search Departments | If there is a department that has the same name that was entered in the fields, the data will be displayed under the Search Results
WS-1.03.006 | Create Department | To create a department, click Create |  | Creation Screen Appears
WS-1.03.007 | Create Department | Select either Create New or Select an existing organization to define as a Department |  | Selection Successful
WS-1.03.008 | Department Description | Enter effective Start Date, Department Set, Name, Internal Address Line, Status, Action Reason, Location and attachments. |  | Information Entry Successful
WS-1.03.009 | Create Department | To access the Department Details page, click Next |  | Department Details Screen Appears
WS-1.03.010 | Create Department | Enter Additional Department Details |  | Information Entry Successful
WS-1.03.011 | Submit New Department | To submit the new department, click Submit. |  | Submission warning Appears
WS-1.03.012 | Submit New Department | To continue with submitting the department, click Yes |  | Submission Successful
WS-1.03.013 | Save New Department | To confirm the request, click OK |  | Save Successful

## 1.04
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Job Families
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.04
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Job Families
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.04.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.04.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | Search successful
WS-1.04.003 | Navigation | Click on task name - 'Manage Job Families' to navigate to task |  | Manage Job Families Page will Appear
WS-1.04.004 | Search Job Families | To see if a job family with the same name has already been entered, enter the Job Families name into the search box. Click Search |  | Search successful
WS-1.04.005 | Create A Job Family | To create a job family, click Create |  | Creation Page Appears
WS-1.04.006 | Create A Job Family | Enter the Effective Start Date, Name, Context Value, Attachment, Action Reason and Status |  | Information Entry Successful
WS-1.04.007 | Submit a Job Family | To submit the new job family, click Submit |  | Warning Window Appears
WS-1.04.008 | Submit a Job Family | Click Yes |  | Confirmation Window Appears
WS-1.04.009 | Save a Job Family | Click OK |  | Save Successful
WS-1.04.010 | Edit Job Family | To edit the Job Family, enter the Name into the field |  | Information Entry Successful
WS-1.04.011 | Edit Job Family | To update or correct the job family, click Edit |  | Edit Screen Appears
WS-1.04.012 | Save Edit to Job Family | Once the Job Family was updated or corrected, click Done |  | Save Successful

## 1.05
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Jobs
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.05
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Jobs through Implementation Projects
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.05.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.05.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.05.003 | Navigation | Click on task name - 'Manage Jobs' to navigate to task |  | The Implementation Project page appears
WS-1.05.004 | Enter Manage Job into the search box | Click Search, by entering any existing Job Name |  | Search successful
WS-1.05.005 | View Manage Job Page | Click on task name to navigate to task |  | Search successful
WS-1.05.006 | Create Job | Click Create |  | Create Job page appeared
WS-1.05.007 | Enter Basic Details | 1) Enter the Effective Start Date 2) Select the Job Set 3) Enter the Name 4) Enter the Code 5) Click Next |  | Create the Basic Details
WS-1.05.008 | Enter Job Description | 1) Select Status 2) Select any additional information from the appropriate dropdowns. |  | Create Job Description
WS-1.05.009 | Enter Job Information | Enter appropriate information into the Job Information fields |  | Create Job Information
WS-1.05.010 | Add Valid Grades | 1) Click Add Row 2) Select Grade from dropdown Note: Perform above steps, if applicable |  | Add Valid Grades
WS-1.05.011 | Go to the Evaluation Criteria Page | Click Next |  | Evaluation Criteria page is displayed
WS-1.05.012 | Enter Evaluation Criteria | 1) Select Evaluation System from dropdown 2) Enter Evaluation Date 3) Select Measurement Unit from dropdown 4) Click Next Note: Perform above steps, if applicable |  | Create Evaluation Criteria
WS-1.05.013 | Add Existing Profile | 1) Click Add Existing Profile 2) Select Profile from the dropdown 3) Enter the Effective Start Date Note: Perform above steps, if applicable |  | Add Existing Profile
WS-1.05.014 | Create Profile | 1) Enter code into the field 2) Click OK 3) Enter the Effective Start Date Note: Perform above steps, if applicable |  | Create Profile
WS-1.05.015 | Go to the Review page | Click Next |  | Review page is displayed
WS-1.05.016 | Submit the new job | 1) Click Submit 2) Click Yes 3) Click OK | 1) Click Submit 2) Click Yes 3) Click OK | The new job has been created

## 1.06
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Grades
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.06
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Grades through Implementation Projects
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.06.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.06.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.06.003 | Navigation | Click on task name - 'Manage Grades' to navigate to task |  | The Implementation Project page appears
WS-1.06.004 | Create Grade | To create a grade, click Create |  | Creation Page Appears
WS-1.06.005 | Create Grade | Enter the effective Start Date, Grade Set, Name, Code, Status, Action Reason, Sort Order, Context and attachments |  | Information Entry Successful
WS-1.06.006 | Create Grade | To access the Grade Steps page, click Next and enter applicable Grade Step details |  | Grade Steps Page Appears
WS-1.06.007 | Create Grade | To access the Grade Rates page, click Next and enter applicable Grade Rates |  | Grade Rates Page Appears
WS-1.06.008 | Create Grade | To access the Review page, click Next |  | Review Page Appears
WS-1.06.009 | Submit Grade | To submit the grade, click Submit. |  | Warning Window Appears
WS-1.06.010 | Submit Grade | To continue with submitting the request, click Yes |  | Submission Successful
WS-1.06.011 | Save Grade | To confirm the request was submitted, click OK |  | Save Successful
WS-1.06.012 | View Grade | To view the new grade, enter the name into the search box. |  | Search successful
WS-1.06.013 | View Grade | To view the grade, click the grade displayed under the Search Results |  | View Results Successful
WS-1.06.014 | Return to the overview page | To return to the Overview page, click Done | To return to the Overview page, click Done | Return To the Overview Page

## 1.07
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Grade Rates
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.07
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Grade Rates through the Functional Setup Manager
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.07.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.07.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | Search successful
WS-1.07.003 | Navigation | Click on task name - 'Manage Grade Rates' to navigate to task |  | Manage Grades Page will Appear
WS-1.07.004 | Create Grade Rate | To create a grade rate, click Create |  | Creation Page Appears
WS-1.07.005 | Create Grade Rate | 1) Click the Legislative Data Group dropdown 2) Click OK |  | Create Grade Rate page appears
WS-1.07.006 | Create Grade Rate | Enter the effective Start Date, Grade Set, Name, Code, Status, Action Reason, Context and attachments |  | Information Entry Successful
WS-1.07.007 | Create Grade Rate Values | 1) To add a grade rate value, click the Add Row 2) To select a grade, click the Grade dropdown 3) Enter the Minimum into the field 4) Enter the Maximum into the field 5) Enter the Midpoint into the field 6) Enter the Value into the field |  | The Grade Rate Value is added successfully
WS-1.07.008 | Create Grade | To access the Review page, click Review |  | Review Page Appears
WS-1.07.009 | Submit Grade | To submit the grade, click Submit. |  | Warning Window Appears
WS-1.07.010 | Submit Grade | To continue with submitting the request, click Yes |  | Submission Successful
WS-1.07.011 | Save Grade | To confirm the request was submitted, click OK |  | Save Successful
WS-1.07.012 | View Grade | To view the new grade, enter the name into the search box. |  | Search successful
WS-1.07.013 | View Grade | To view the grade, click the grade displayed under the Search Results |  | View Results Successful
WS-1.07.014 | Return to the overview page | To return to the Overview page, click Done |  | Return To the Overview Page

## 1.08
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Position
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.08
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Position Through Implementation Projects
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.08.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.08.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.08.003 | Navigation | Click on task name - 'Manage Positions' to navigate to task |  | The Implementation Project page appears
WS-1.08.004 | Create Position | To create a Position, click Create |  | Creation Page Appears
WS-1.08.005 | Basic Details | 1) Enter Effective Start Date into the field 2) Select the Business Unit from the dropdown 3) Enter the Name into the field 4) Enter the Code into the field 5) To go to the Position Details page, click Next |  | The Basic Details have been entered
WS-1.08.006 | Position Details | 1) Select the Status from the dropdown 2) Select the Department from the dropdown 3) Select the Job from the dropdown 4) Select the Hiring Status from the dorpdown 5) Enter additional details into the fields 6) To go to the Evaluation Criteria page, click Next |  | The Position Details have been entered
WS-1.08.007 | Evaluation Criteria | 1) Select the Evaluation System dropdown 2) Enter the Evaluation Date 3) Select the Measurement Unit from the dropdown 4) Click Next Note: Perform above steps, if applicable |  | The Evaluation Criteria has been entered
WS-1.08.008 | Profiles | 1) To add a profile to the position select Add Existing Profile or Create Profile 2) Enter the appropriate information into the fields 3) Click Next Note: Perform above steps, if applicable |  | The Profiles have been entered
WS-1.08.009 | Review | 1) To submit the Position, click Submit 2) Click Yes 3) Click OK 4) To go back to the Overview page, click Done |  | The Position has been created

## 1.09
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Organization Trees
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.09
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Organization Trees
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.09.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.09.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | Search successful
WS-1.09.003 | View Organization Trees Page | Click on task name - 'Manage Organization Trees' to navigate to task |  | Search successful
WS-1.09.004 | Create Organization Tree | Click Create |  | Specify Definition page is displayed
WS-1.09.005 | Enter Specify Definition Information | 1) Enter the Name 2) Enter the Code 3) Click Next |  | Create the Specify Definition Information
WS-1.09.006 | View Specify Labels | View Specify Labels page Click Next |  | View Specify Labels page
WS-1.09.007 | Submit the Organization Tree | 1) Click Submit 2) Click Yes 3) Click OK |  | The new organization tree has been created
WS-1.09.008 | Create Tree Version | 1) Select the organization tree created in earlier step 2) Click Actions 3) Click Create Version |  | Manage Organization Tree: Specify Definition page is displayed
WS-1.09.009 | Enter Specify Definition Information | 1) Enter the Name 2) Enter the Effective Start Date 3) Click Next 4) Click OK |  | Create the Specify Definition Information
WS-1.09.010 | Search for Tree Node Details | 1) Click Search 2) Enter the Name into the field 3) Click Search 4) Select the appropriate tree node 5) Click Add Tree Node |  | Create Tree Node Details
WS-1.09.011 | Click Submit | 1) Click Submit 2) Click Yes 3) Click OK |  | The new specify node has been created.
WS-1.09.012 | Change status to Active | 1) Click Actions 2) Click Flatten 3) Click Row Flattening 4) Click Online Flattening 5) Click OK 6) Click Done 7) Select the organization tree row 8) Click Actions 9) Click Audit 10) Click Online Audit 11) Click OK 12) Click Done 13) Select the organization tree row 14) Click Actions 15) Click Set Status 16) Click Active 17) Click OK |  | The status is changed to Active

## 1.10
System Test Script - Oracle HCM Cloud - Global HR
Generate Organization Hierarchy Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.10
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Organization Hierarchy Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.10.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.10.02 | Navigate to Navigator | Navigate to the below path: Homepage > OD Reports (Tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.10.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.10.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.10.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The Organization report will display all the levels of the department and the number of positions and assigments as per budgets and actuals. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.11
System Test Script - Oracle HCM Cloud - Global HR
Generate Workforce Planning Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.11
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Workforce Planning Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.11.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.11.02 | Navigate to Navigator | Navigate to the below path: Homepage > OD Reports (Tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.11.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.11.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.11.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The Workforce Planning report will display all the positions and the incumbents as per the employee and position details currently available in the system. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.12
System Test Script - Oracle HCM Cloud - Global HR
Generate Manpower Budget Headcount Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.12
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Manpower Budget Headcount Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.12.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.12.02 | Navigate to Navigator | Navigate to the below path: Homepage > OD Reports (Tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.12.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.12.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.12.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The Manpower budget report will display totals of the positions and the incumbents as per the category (SA, WE, EE etc) for each quarter as we proceed through the year. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.13
System Test Script - Oracle HCM Cloud - Global HR
Generate Salary Beyond the Range Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.13
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Salary Beyond the Range Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.13.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.13.02 | Navigate to Navigator | Navigate to the below path: Homepage > OD Reports (Tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.13.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.13.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.13.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The salary beyond the range report will display all the employees who has a salary basis attached the salary is outside the limits of the salary range for the grade. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.14
System Test Script - Oracle HCM Cloud - Global HR
Generate Missing Department Managers Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.14
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Missing Department Managers Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.14.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.14.02 | Navigate to Navigator | Navigate to the below path: Homepage > OD Reports (Tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.14.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.14.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.14.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report should display all the employees who do not report to the managers of job level 8/9. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.15
System Test Script - Oracle HCM Cloud - Global HR
Generate Missing Line Managers Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.15
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Missing Line Managers Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.15.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.15.02 | Navigate to Navigator | Navigate to the below path: Homepage > OD Reports (Tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.15.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.15.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.15.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report should display all the employees who do not have a line manager available in the system. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.16
System Test Script - Oracle HCM Cloud - Global HR
Generate Previous Experience Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.16
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Previous Experience Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.16.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.16.02 | Navigate to Navigator | Navigation Steps: Homepage > OD Reports (tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.16.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.16.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.16.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report will display all the employees along with their previous employment history from the Previous Employment content type. | Download the report | Report should be generated without any errors or data discrepancies. | Report should be generated without any errors or data discrepancies.
Download the report by selcting the excel as an option,

## 1.17
System Test Script - Oracle HCM Cloud - Global HR
Generate Performance Rating Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.17
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Performance Rating Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.17.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.17.02 | Navigate to Navigator | Navigation Steps: Homepage > OD Reports (tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.17.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.17.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.17.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report will display all the employees along with their performance ratings stored as the content types under skills and qualifications. | Download the report | Report should be generated without any errors or data discrepancies. | Report should be generated without any errors or data discrepancies.
Download the report by selcting the excel as an option,

## 1.18
System Test Script - Oracle HCM Cloud - Global HR
Generate Employee Attrition Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.18
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Employee Attrition Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.18.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.18.02 | Navigate to Navigator | Navigation Steps: Homepage > OD Reports (tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.18.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.18.04 | Employee Selection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.18.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report will display all the employees along with their performance ratings stored as the content types under skills and qualifications. | Download the report | Report should be generated without any errors or data discrepancies. | Report should be generated without any errors or data discrepancies.
Download the report by selcting the excel as an option,

## 1.19
System Test Script - Oracle HCM Cloud - Global HR
Generate Manpower Report Monthly
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.19
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Manpower Report Monthly
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.19.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.19.02 | Navigate to Navigator | Navigation Steps: Homepage > OD Reports (tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.19.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.19.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.19.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report will display all the employees along with their performance ratings stored as the content types under skills and qualifications. | Download the report | Report should be generated without any errors or data discrepancies. | Report should be generated without any errors or data discrepancies.
Download the report by selcting the excel as an option,

## 1.20
System Test Script - Oracle HCM Cloud - Global HR
Generate Annual Budget Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.20
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Annual Budget Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.20.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.20.02 | Navigate to Navigator | Navigation Steps: Homepage > OD Reports (tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.20.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.20.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.20.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report will display all the employees along with their performance ratings stored as the content types under skills and qualifications. | Download the report | Report should be generated without any errors or data discrepancies. | Report should be generated without any errors or data discrepancies.
Download the report by selcting the excel as an option,

## 1.21
System Test Script - Oracle HCM Cloud - Global HR
Manage Costing of Departments
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.21
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Manage Costing of Departments
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.21.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.21.02 | Navigate to Navigator | Navigation Steps: Homepage > My Client Groups (tab) > Click Manage Costing of Departments (under Payroll) |  | User should be able to navigate to the task | User should be able to navigate to the task
WS-1.21.03 | Open the task | Click on the link for the task to see the Manage Costing of Departments page |  | Open the task without any issues | Open the task without any issues
WS-1.21.04 | Department Selection | I nthe Manage Costing of Departments page, enter the department for which the costing details have to be added. Legislative Data Group would be SA Legislative Data Group |  | Enter the search criteria and Search. The results should display the department. | Enter the search criteria and Search. The results should display the department.
WS-1.21.05 | Add Costing detail | If the department already has the costing, results are shown as hyperlink. Otherwise, the department name will not be shown as a link. |  | The user should be able to add the costing detail without any errors. | The user should be able to add the costing detail without any errors.
Select the department to add costing and click Create For existing departments, click Edit > Correct/Update appropriately.
Enter the effective date of the costing.
Click + (Create) to add new costing detail.
Enter the following details and click Submit 1. Percentage - Usually 100% unless one department cost is split into multiple cost centers 2. Company 3. Division 4. Cost Center 5. Analytical Code

## 1.22
System Test Script - Oracle HCM Cloud - Global HR
Generate Assignment History Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.22
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Assignment History Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.20.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.20.02 | Navigate to Navigator | Navigation Steps: Homepage > OD Reports (tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.20.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.20.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.20.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report will display all the employees along with their performance ratings stored as the content types under skills and qualifications. | Download the report | Report should be generated without any errors or data discrepancies. | Report should be generated without any errors or data discrepancies.
Download the report by selcting the excel as an option,

## 1.23
System Test Script - Oracle HCM Cloud - Global HR
Generate Salary History Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.23
Pilot / SIT# / UAT# |  | User Acceptance Testing (UAT) | Test Script Name | Generate Salary History Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.20.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
WS-1.20.02 | Navigate to Navigator | Navigation Steps: Homepage > OD Reports (tab) |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
WS-1.20.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
WS-1.20.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
WS-1.20.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report will display all the employees along with their performance ratings stored as the content types under skills and qualifications. | Download the report | Report should be generated without any errors or data discrepancies. | Report should be generated without any errors or data discrepancies.
Download the report by selcting the excel as an option,