## Effort Plan
| Categorize of Test Cases(basis of test steps) | HCM Estimated Test Cases | Effort Plan(no. of days) | Buffer
| Simple TC | 49 | 49 | 5 days
| Medium TC | 5 | 6.25
| Complex TC | 11 | 16.5
| Very Complex TC | 6 | 24
| Total TC | 71 | 95.75
| Test Cases | Description
| Simple | Test Cases < 20 steps
| Medium | Test Cases > than 20 steps < 25 steps
| Complex | Test Cases > 25 steps< 80 steps
| Very Complex | Test Cases >80 steps <125 steps
Note: - | 1) All total 71 TCs provided by HCM lead(Ravi). 2) There are 3 TCs which includes over 80 steps(81,82,91) and 3 TCs over 100 steps(100,125,125). However I can create multi scenarios on this TCs while I will design the script. This might be increase/ decrease the effort plan accordingly. 3) The effort plan includes, application knowledge gathering and Test data creation before script design. 4) Test Design Start date would be next week –> Expected start date- 20/21-April-20 (Depending on environmental ready) Environment:- a) OATS installation in IBM machine - Done b) Access to the HCM cloud with my own credential - Pending with Ravi 5) Target delivery –> 15-18 Scenarios P/M(rest 2-5 scenario from EBS application- Still some scenarios are pending, once it will completed, full focus will switch to HCM cloud application)

## HCM TC
Test Script Summary
Test Script Summary |  | Test Results
ID # | Test Script Name | Date Tested | Tested By | Test Status | Notes
New Hire
1.01 | Hiring an Employee |  |  |  | 125 Steps
New Contingent Worker
2.01 | Adding a Contingent Worker |  |  |  | 122 steps
New Pending Worker
3.01 | Create a Pending Worker |  |  |  | 91 steps
3.02 | Convert a Pending Worker to Employee
Manage Person
4.01 | Name Correction
4.02 | Name Update |  |  |  | 22 Steps
4.03 | Address Correction |  |  |  | 22 Steps
4.04 | Address Update |  |  |  | 23 Steps
4.05 | Add Secondary Address |  |  |  | 25 steps
4.06 | Add New Emergency Contact Information |  |  |  | 42 Steps
4.07 | Add an Existing Employee as an Emergency Contact |  |  |  | 21 Steps
4.08 | Modify Existing Emergency Contact |  |  |  | 29 steps
Manage Employment
5.01 | Enter Status Change |  |  |  | 26 Steps
5.02 | Enter Manager Change |  |  |  | 26 Steps
5.03 | Enter Job Change |  |  |  | 26 Steps
5.04 | Correct Information |  |  |  | 26 Steps
5.05 | Contract Extension/Updates |  |  |  | 26 Steps
Suspend an Employee
6.01 | Manage Employment - Assignment Status Change |  |  |  | 26 Steps
Terminate Employee
7.01 | Terminate an Employee |  |  |  | 26 Steps
Manage Identification Information
8.01 | Add/Edit Passport Information
8.02 | Add/Edit Visa/Work Permit Information
8.03 | Add/Edit Civil ID Information
Terminate Contingent Worker
9.01 | Terminate a Contingent Worker |  |  |  | 24 Steps
Reverse Termination
10.01 | Reversing a Termination
Rehire Employee
11 | Rehiring a Terminated Employee |  |  |  | 82 Steps
Contingent Worker to Employee
12.01 | Convert a Contingent Worker to an Employee |  |  |  | 100 Steps
Enter Content Types
13.01 | Employee Create Profile Content Type Information
Create Work Relationship
14.01 | Manually Creating a Work Relationship for a Person |  |  |  | 81 Steps
Pending Worker Work Relationship
15.01 | Cancel Work Relationship of Pending Worker
Manage Checklists - Clearance Checklists
16.01 | Manage Checklists - Clearance Checklists
Manage Checklists - Notifications and Tasks
17.01 | Manage Checklists - Task Exit Clearance
Reports, Letters and Notifications
18.01 | Embassy Certificate
19.01 | Employment Certificate
20.01 | Experience Certificate
21.01 | Housing Proof Certificate
22.01 | No Objection Certificate
23.01 | Generate Dependent's Report
24.01 | Generate Previous Experience Report
25.01 | Generate Performance Rating Report
26.01 | Generate Time Attendance Report
27.01 | Generate Employee Attrition Report
28.01 | Probation Appraisal Notification
29.01 | Service Contract Extension Notification
30.01 | Retirement Notification
31.01 | Passport Expiry Notification
32.01 | Iqama Expiry Notification
33.01 | Civil ID Number Expiry Notification
Retirement Extension Request
34.01 | Contract Extension for Retirement Employees (> 60 yrs)
Retirement Extension (Manual)
35.01 | Retirement Extension
Manager Self Service |  |  |  |  | 25 Steps
1.01 | Service Contract Extension
1.02 | Submit Resignation or Termination for a direct report
1.03 | View Skills and Qualifications |  |  |  | Line Managers will be able to see the following a) Performance Rating History b) Previous Employment c) Languages
1.04 | Contract Extension for Retirement Employees (> 60 yrs)
Manager Self Service
1.01 | Edit Phones/Email Address
1.02 | Update Home Address
1.03 | Create a New Address
1.04 | Change Personal Details
1.05 | Manage Contact Information
1.06 | Manage Family or Emergency Contacts
1.07 | Manage Biographical Information
1.08 | Certificate Requests
1.09 | Add Previous Employment
1.1 | Add Trainings |  |  |  | Trainings have been discarded for the HR project. They will be configured at the time of Talent Management
1.11 | Add Qualifications |  |  | NA | Qualifications have been discarded for the HR project. They will be configured at the time of Talent Management
1.12 | Manage Document Records |  |  | NA | There is a nother test script created for Exit Interview Questionnaire.
1.13 | Submit Resignation
1.14 | Add/Edit Passport Information
1.15 | Add/Edit Visa or Work Permits Information
Person Spotlight
2.01 | View in Organizational Chart
2.02 | Update Areas of Expertise
Exit Interview
3.01 | Submit Exit Interview Questionnaire |  |  |  |  | 71