## HCM Test Scripts
Test Script Names | Test Cases | Scenarios | Expected Start Date | Expected End Date
Core HR
TE.025 - Test Script - HCM Cloud - Global HR - Employee Relations_V1.1 | 50 | 70 | 2020-07-01 | 2020-11-10
TE.025 - Test Script - HCM Cloud - Global HR - Employee Self-Service_V1.1 | 18 | 27 | 2020-11-11 | 2020-11-18
TE.025 - Test Script - HCM Cloud - Global HR - Manager Self-Service_V1.1 | 4 | 5 | 2020-11-19 | 2020-11-23
TE.025 - Test Script - HCM Cloud - Global HR - Organization Development_V1.1 | 23 | 41 | 2020-11-24 | 2021-01-25
Absence
Maaden - TE.025 - Absence Management - ESS - UAT | 41 | 60 | 2021-01-26 | 2021-04-26
Maaden - TE.025 - Absence Management - HR - UAT | 2 | 2 | 2021-04-27 | 2021-04-29
Maaden - TE.025 - Absence Management - MSS - UAT | 42 | 60 | 2021-04-30 | 2021-07-30
Total | 180 | 265
Note : -
1) Above scenarios are 70% of total HCM test cases. 2) Above test cases excluding payroll Module. 3) Total effort will be required to design full scenario per resource is around 265 days.(+/- 10 days) 4) Estimation has given on the basis of 20 scenarios deliverables per month.

## Organization Development1
Total Test Cases | Total Scenarios
HCM_ManageLocations_EditLocation_0030
HCM_ManageLocations_CorrectionLocation_0031
HCM_ManageLocations_CreateLocation_0032
HCM_ManageJobs_CreateNewDivision_0039
HCM_ManageJobs_CreateDivision_AnExistingOrganization_0040
HCM_ManageJobs_EditDivision_UpdateOption_0041
HCM_ManageJobs_EditDivision_CorrectOption_0042
HCM_ManageDepartments_CreateDepartment_0043
HCM_ManageDepartments_Create_ExistingDepartment_0044
HCM_ManageDepartments_EditDepartment_0045
HCM_ManageJobFamilies_Create_JobFamilies_0033
HCM_ManageJobFamilies_Update_JobFamilies_0034
HCM_ManageJobFamilies_Correct_JobFamilies_0035
HCM_ManageJobs_CreateJobs_WO_Grades_0036
HCM_ManageJobs_CreateJobs_CreateProfile_0037
HCM_ManageJobs_CreateJobs_AddExistingProfile_0038
HCM_Manage Grades_CreateGrade_0046
HCM_Manage Grades_CreatedulpicateGrades_0047
HCM_ManageGrades_EditGrades_0048
HCM_ManageGrades_Edit_CorrectGrades_0049
HCM_ManageGradeRates_CreateGradeRates_0050
HCM_ManageGradeRates_CreateduplicateGradeRates_0051
HCM_ManageGradeRates_UpdateGradeRates_0052
HCM_ManageGradeRates_CorrectGradeRates_0053
HCM_ManagePosition_CreatePosition_0054
HCM_ManagePosition_CreatePosition_With_ExistingProfile_0055
HCM_ManagePosition_UpdatePosition_0056
HCM_ManagePosition_CorrectPosition_0057
HCM_GenerateOrganizationHierarchyReport_0058
HCM_GenerateWorkforcePlanningReport_0059
HCM_GenerateSalaryBeyondtheRangeReport_0060
HCM_GenerateMissingDepartmentManagersReport_0061
HCM_GenerateMissingLineManagersReport_0062
HCM_ManageCostingDepartments_0063
HCM_Edit_CostingDepartments_0064
HCM_Delete_CostingDepartments_0065
HCM_Correct_CostingDepartments_0066

## Organization Development
System Test Script - Oracle HCM Cloud - Organization Development
Test Cases | TestScript Name | Status/Comments
Manage Locations | HCM_ManageLocations_EditLocation_0030 HCM_ManageLocations_CorrectionLocation_0031 HCM_ManageLocations_CreateLocation_0032 | Done
Manage Divisions | HCM_ManageJobs_CreateNewDivision_0039 HCM_ManageJobs_CreateDivision_AnExistingOrganization_0040 HCM_ManageJobs_EditDivision_UpdateOption_0041 HCM_ManageJobs_EditDivision_CorrectOption_0042 | Done
Manage Departments | HCM_ManageDepartments_CreateDepartment_0043 HCM_ManageDepartments_Create_ExistingDepartment_0044 HCM_ManageDepartments_EditDepartment_0045 | Done
Manage Job Families | HCM_ManageJobFamilies_Create_JobFamilies_0033 HCM_ManageJobFamilies_Update_JobFamilies_0034 HCM_ManageJobFamilies_Correct_JobFamilies_0035 | Done
Manage Job | HCM_ManageJobs_CreateJobs_WO_Grades_0036 HCM_ManageJobs_CreateJobs_CreateProfile_0037 HCM_ManageJobs_CreateJobs_AddExistingProfile_0038 | Done
Manage Grades | HCM_Manage Grades_CreateGrade_0046 HCM_Manage Grades_CreatedulpicateGrades_0047 HCM_ManageGrades_EditGrades_0048 HCM_ManageGrades_Edit_CorrectGrades_0049 | Done
Manage Grade Rates | HCM_ManageGradeRates_CreateGradeRates_0050 HCM_ManageGradeRates_CreateduplicateGradeRates_0051 HCM_ManageGradeRates_UpdateGradeRates_0052 HCM_ManageGradeRates_CorrectGradeRates_0053 | Done
Manage Position | HCM_ManagePosition_CreatePosition_0054 HCM_ManagePosition_CreatePosition_With_ExistingProfile_0055 HCM_ManagePosition_UpdatePosition_0056 HCM_ManagePosition_CorrectPosition_0057 | Done
Manage Organization Trees | Not Covered | Data Not Available
Generate Organization Hierarchy Report | HCM_GenerateOrganizationHierarchyReport_0058 | Done
Generate Workforce Planning Report | HCM_GenerateWorkforcePlanningReport_0059 | Done
Generate Manpower Budget Headcount Report | Not Covered | Ravi Said not required as of now
Generate Salary beyond the range report | HCM_GenerateSalaryBeyondtheRangeReport_0060 | Done
Generate Missing Department Managers Report | HCM_GenerateMissingDepartmentManagersReport_0061 | Done
Generate Missing Line Managers Report | HCM_GenerateMissingLineManagersReport_0062 | Done
Generate Previous Experience Report | Not Covered | Ravi Said not required as of now
Generate Performance Rating Report | Not Covered | Ravi Said not required as of now
Generate Employee Attrition Report | Not Covered | Ravi Said not required as of now
Generate Manpower Report Monthly | Not Covered | Ravi Said not required as of now
Generate Annual Budget Report | Not Covered | Ravi Said not required as of now
Manage Costing of Departments | HCM_ManageCostingDepartments_0063 HCM_Edit_CostingDepartments_0064 HCM_Delete_CostingDepartments_0065 HCM_Correct_CostingDepartments_0066 | Done
Generate Assignment History Report | Not Covered | Ravi Said not required as of now
Generate Salary History Report | Not Covered | Ravi Said not required as of now