## HCM Test Scripts
| Projected |  | Actual
Test Script Names | Test Cases | Scenarios | Automation Script Created(Scenarios) | Pending/Skipped(TC) | Coverage % | Expected Start Date | Expected End Date | Comments
Core HR
TE.025 - Test Script - HCM Cloud - Global HR - Employee Relations_V1.1 | 50 | 70 | 12 | 48 | 17.1429 | 2020-07-01 | 2020-11-10 | 9 scenario created w.r.t 20C
TE.025 - Test Script - HCM Cloud - Global HR - Employee Self-Service_V1.1 | 18 | 27 | 38 | 6 | 140.7407 | 2020-11-11 | 2020-11-18 | 4 scenario Pending 2 scenarios absolute
TE.025 - Test Script - HCM Cloud - Global HR - Manager Self-Service_V1.1 | 4 | 5 | 0 | 4 | 0 | 2020-11-19 | 2020-11-23
TE.025 - Test Script - HCM Cloud - Global HR - Organization Development_V1.1 | 23 | 41 | 41 | 9 | 100 | 2020-11-24 | 2021-01-25 | 8-Ravi said not required at this moment 1-Test data not available. Confirmed by Shreya
Absence
Maaden - TE.025 - Absence Management - ESS - UAT | 41 | 60 | 0 | 41 | 0 | 2021-01-26 | 2021-04-26
Maaden - TE.025 - Absence Management - HR - UAT | 2 | 2 | 0 | 2 | 0 | 2021-04-27 | 2021-04-29
Maaden - TE.025 - Absence Management - MSS - UAT | 42 | 60 | 0 | 42 | 0 | 2021-04-30 | 2021-07-30
Total | 180 | 265 | 91 | 154
Note : -
1) Above scenarios are 70% of total HCM test cases. 2) Above test cases excluding payroll Module. 3) Total effort will be required to design full scenario per resource is around 265 days.(+/- 20 days) 4)This is a projection, once the script will start creating, the figure might be change. 5) Estimation has given on the basis of 20 scenarios deliverables per month.