## Summary
System Test Script - Oracle HCM Cloud - Organization Development
Test Script Summary
Overview
Software / Release |  | HCM Cloud Release 13 |  |  | Note - The value entered propagates across all worksheets
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) |  |  | Note - The value entered propagates across all worksheets
Test Script Summary |  | Test Results
ID # | Test Script Name | Date Tested | Tested By | Test Status | Notes
Global HR - Admin Tests
1.01 | Manage Business Unit
1.02 | Manage Locations
1.03 | Manage Divisions
1.04 | Manage Departments
1.05 | Manage Job Families
1.06 | Manage Job
1.07 | Manage Grades
1.08 | Manage Grade Rates
1.09 | Manage Position
1.10 | Manage Organization Trees
1.11 | Generate Organization Hierarchy Report
1.12 | Generate Workforce Planning Report
1.13 | Generate Manpower Budget Report
1.14 | Generate Salary beyond the range report
1.15 | Generate Missing Department Managers Report
1.16 | Generate Missing Line Managers Report

## 1.01
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Business Unit
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.01
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Business Unit
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.01.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.01.002 | Enter Manage Business Unit | Click on tasklist icon present on the right side of the application window. |  | Search successful
WS-1.01.003 | View the Manage Business Unit Page | Click on task name - 'Manage Business Unit' to navigate to task |  | Navigation successful
WS-1.01.004 | Search existing Business Unit | Enter the Business Unit name into the search box, Click Search |  | Search successful
WS-1.01.005 | View Business Unit | If there is a business unit that has the same name that was entered in the field, the data will be displayed under the Search Results |  | Results Display Successful
WS-1.01.006 | Edit Business Unit | To open a business unit, click on the Business Unit name |  | Information Display Successful
WS-1.01.007 | Edit Business Unit | Edit Desired Business Unit information by selecting Edit |  | Edit Screen Appears
WS-1.01.008 | Edit Business Unit | Edit desired fields |  | Edit Successful
WS-1.01.009 | Submit Edit of Business Unit | Click Save and Close |  | Submit window appears
WS-1.01.010 | Enter Manage Business Unit | Enter Manage Business Unit in the Search Field |  | Search successful
WS-1.01.011 | View the Manage Business Unit Page | Click on task name to navigate to task |  | Navigation successful
WS-1.01.012 | Create Business Unit | Click Create Icon |  | Entry page displays
WS-1.01.013 | Create Business Unit | Enter Name, Manager, Location, Default Set information |  | Information Entry Successful
WS-1.01.014 | Save Business Unit | Click Save and Close |  | Save Successful

## 1.02
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Locations
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.02
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Locations through Implementation Project
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.02.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.02.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.02.003 | Navigation | Click on task name - 'Manage Locations' to navigate to task |  | The Implementation Project page appears
WS-1.02.004 | Search Location | To search for an existing Location, enter the name into the search box |  | Search successful
WS-1.02.005 | View Location | If there is a location that has the same name that was entered in the field, the data will be displayed under the Search Results |  | Results Display Successful
WS-1.02.006 | Edit Location | To update or correct the location, click Edit Icon |  | Edit Screen Appears
WS-1.02.007 | Edit Location | Select Effective Start Date, Click OK |  | Edit Screen Appears
WS-1.02.008 | Edit Location | Edit desired location information by selecting Edit |  | Edit Screen Appears
WS-1.02.009 | Save location edits | Click Submit |  | Submit window appears
WS-1.02.010 | Save location edits | Click Yes |  | Confirmation Window appears
WS-1.02.011 | Save location edits | Click OK |  | Save Successful
WS-1.02.012 | Save location edits | Click Done to return to overview page |  | Return Successful
WS-1.02.013 | Create new location | Click Create |  | Creation Screen Appears
WS-1.02.014 | Create new location | Enter the effective start date into the field |  | Entry Successful
WS-1.02.015 | Create new location | Select Location Set |  | Selection Successful
WS-1.02.016 | Create new location | Enter Location Name, Code and Description into fields | Enter Location Name, Code and Description into fields | Information Entry Successful
WS-1.02.017 | Create new location | Select a status |  | Status selection successful
WS-1.02.018 | Create new location | To select a country, select desired country from drop down menu |  | Desired country information displays
WS-1.02.019 | Create new location | Enter Address Information |  | Information Entry Successful
WS-1.02.020 | Create new location | Enter additional Information |  | Information Entry Successful
WS-1.02.021 | Save new Location | Click Submit |  | Submit window appears
WS-1.02.022 | Save new Location | Click Yes |  | Confirmation Window appears
WS-1.02.023 | Save new Location | Click OK |  | Save Successful
WS-1.02.024 | Save new Location | Click Done to return to overview page |  | Return Successful

## 1.03
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Divisions
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.03
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Divisions through Implementation Project
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.03.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.03.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.03.003 | Navigation | Click on task name - 'Manage Divisions' to navigate to task |  | The Implementation Project page appears
WS-1.03.004 | Search Division | To search for an existing Division, enter the name into the search box |  | Search successful
WS-1.03.005 | View Division | If there is a location that has the same name that was entered in the field, the data will be displayed under the Search Results |  | Results Display Successful
WS-1.03.006 | Edit Division | To update or correct the Division, click Edit Icon |  | Edit Screen Appears
WS-1.03.007 | Edit Division | Select Effective Start Date, Click OK |  | Edit Screen Appears
WS-1.03.008 | Edit Division | Edit Desired Division information |  | Information Entry Successful
WS-1.03.009 | Save Division Edits | Click Submit |  | Submit window appears
WS-1.03.010 | Save Division Edits | Click Yes |  | Confirmation Window appears
WS-1.03.011 | Save Division Edits | Click OK |  | Save Successful
WS-1.03.012 | Save Division Edits | Click Done to return to overview page |  | Return Successful
WS-1.03.013 | Create New Division | Click Create Icon |  | Creation Screen Appears
WS-1.03.014 | Create New Division | Select either create a new division or an existing organization to define as a division |  | Selection Successful
WS-1.03.015 | Create New Division | Enter effective start date |  | Entry Successful
WS-1.03.016 | Create New Division | Enter Division Name, Action Reason, and location | Enter Division Name, Action Reason, and location | Information Entry Successful
WS-1.03.017 | Create New Division | To view the Division Details page, click Next |  | Division Details Screen Appears
WS-1.03.018 | Create New Division | Enter a reporting name into the field |  | Information Entry Successful
WS-1.03.019 | Create New Division | Select Manager from Dropdown list |  | Selection Successful
WS-1.03.020 | Save New Division | Click Submit |  | Submit window appears
WS-1.03.021 | Save New Division | Click Yes |  | Confirmation Window appears
WS-1.03.022 | Save New Division | Click OK |  | Save Successful
WS-1.03.023 | Save New Division | Click Done to return to overview page |  | Return Successful

## 1.04
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Departments
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.04
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Departments through Implementation Project
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.04.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.04.002 | Navigation | Click on tasklist icon present on the right side of the application window. | Click Manage Implementation Projects | The Manage Implementation Projects page appears
WS-1.04.003 | Navigation | Click on task name - 'Manage Departments' to navigate to task |  | The Manage Departments page appears
WS-1.04.004 | Search Departments | Enter the appropriate information into at least one required fields, Click Search |  | Search successful
WS-1.04.005 | Search Departments | If there is a department that has the same name that was entered in the fields, the data will be displayed under the Search Results
WS-1.04.006 | Create Department | To create a department, click Create |  | Creation Screen Appears
WS-1.04.007 | Create Department | Select either Create New or Select an existing organization to define as a Department |  | Selection Successful
WS-1.04.008 | Department Description | Enter effective Start Date, Department Set, Name, Internal Address Line, Status, Action Reason, Location and attachments. |  | Information Entry Successful
WS-1.04.009 | Create Department | To access the Department Details page, click Next |  | Department Details Screen Appears
WS-1.04.010 | Create Department | Enter Additional Department Details |  | Information Entry Successful
WS-1.04.011 | Submit New Department | To submit the new department, click Submit. |  | Submission warning Appears
WS-1.04.012 | Submit New Department | To continue with submitting the department, click Yes |  | Submission Successful
WS-1.04.013 | Save New Department | To confirm the request, click OK |  | Save Successful

## 1.05
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Job Families
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.05
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Job Families
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.05.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.05.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | Search successful
WS-1.05.003 | Navigation | Click on task name - 'Manage Job Families' to navigate to task |  | Manage Job Families Page will Appear
WS-1.05.004 | Search Job Families | To see if a job family with the same name has already been entered, enter the Job Families name into the search box. Click Search |  | Search successful
WS-1.05.005 | Create A Job Family | To create a job family, click Create |  | Creation Page Appears
WS-1.05.006 | Create A Job Family | Enter the Effective Start Date, Name, Context Value, Attachment, Action Reason and Status |  | Information Entry Successful
WS-1.05.007 | Submit a Job Family | To submit the new job family, click Submit |  | Warning Window Appears
WS-1.05.008 | Submit a Job Family | Click Yes |  | Confirmation Window Appears
WS-1.05.009 | Save a Job Family | Click OK |  | Save Successful
WS-1.05.010 | Edit Job Family | To edit the Job Family, enter the Name into the field |  | Information Entry Successful
WS-1.05.011 | Edit Job Family | To update or correct the job family, click Edit |  | Edit Screen Appears
WS-1.05.012 | Save Edit to Job Family | Once the Job Family was updated or corrected, click Done |  | Save Successful

## 1.06
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Jobs
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.06
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Jobs through Implementation Projects
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.06.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.06.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.06.003 | Navigation | Click on task name - 'Manage Jobs' to navigate to task |  | The Implementation Project page appears
WS-1.06.004 | Enter Manage Job into the search box | Click Search, by entering any existing Job Name |  | Search successful
WS-1.06.005 | View Manage Job Page | Click on task name to navigate to task |  | Search successful
WS-1.06.006 | Create Job | Click Create |  | Create Job page appeared
WS-1.06.007 | Enter Basic Details | 1) Enter the Effective Start Date 2) Select the Job Set 3) Enter the Name 4) Enter the Code 5) Click Next |  | Create the Basic Details
WS-1.06.008 | Enter Job Description | 1) Select Status 2) Select any additional information from the appropriate dropdowns. |  | Create Job Description
WS-1.06.009 | Enter Job Information | Enter appropriate information into the Job Information fields |  | Create Job Information
WS-1.06.010 | Add Valid Grades | 1) Click Add Row 2) Select Grade from dropdown Note: Perform above steps, if applicable |  | Add Valid Grades
WS-1.06.011 | Go to the Evaluation Criteria Page | Click Next |  | Evaluation Criteria page is displayed
WS-1.06.012 | Enter Evaluation Criteria | 1) Select Evaluation System from dropdown 2) Enter Evaluation Date 3) Select Measurement Unit from dropdown 4) Click Next Note: Perform above steps, if applicable |  | Create Evaluation Criteria
WS-1.06.013 | Add Existing Profile | 1) Click Add Existing Profile 2) Select Profile from the dropdown 3) Enter the Effective Start Date Note: Perform above steps, if applicable |  | Add Existing Profile
WS-1.06.014 | Create Profile | 1) Enter code into the field 2) Click OK 3) Enter the Effective Start Date Note: Perform above steps, if applicable |  | Create Profile
WS-1.06.015 | Go to the Review page | Click Next |  | Review page is displayed
WS-1.06.016 | Submit the new job | 1) Click Submit 2) Click Yes 3) Click OK | 1) Click Submit 2) Click Yes 3) Click OK | The new job has been created

## 1.07
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Grades
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.07
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Grades through Implementation Projects
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.07.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.07.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.07.003 | Navigation | Click on task name - 'Manage Grades' to navigate to task |  | The Implementation Project page appears
WS-1.07.004 | Create Grade | To create a grade, click Create |  | Creation Page Appears
WS-1.07.005 | Create Grade | Enter the effective Start Date, Grade Set, Name, Code, Status, Action Reason, Sort Order, Context and attachments |  | Information Entry Successful
WS-1.07.006 | Create Grade | To access the Grade Steps page, click Next and enter applicable Grade Step details |  | Grade Steps Page Appears
WS-1.07.007 | Create Grade | To access the Grade Rates page, click Next and enter applicable Grade Rates |  | Grade Rates Page Appears
WS-1.07.008 | Create Grade | To access the Review page, click Next |  | Review Page Appears
WS-1.07.009 | Submit Grade | To submit the grade, click Submit. |  | Warning Window Appears
WS-1.07.010 | Submit Grade | To continue with submitting the request, click Yes |  | Submission Successful
WS-1.07.011 | Save Grade | To confirm the request was submitted, click OK |  | Save Successful
WS-1.07.012 | View Grade | To view the new grade, enter the name into the search box. |  | Search successful
WS-1.07.013 | View Grade | To view the grade, click the grade displayed under the Search Results |  | View Results Successful
WS-1.07.014 | Return to the overview page | To return to the Overview page, click Done | To return to the Overview page, click Done | Return To the Overview Page

## 1.08
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Grade Rates
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.08
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Grade Rates through the Functional Setup Manager
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.08.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.08.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | Search successful
WS-1.08.003 | Navigation | Click on task name - 'Manage Grade Rates' to navigate to task |  | Manage Grades Page will Appear
WS-1.08.004 | Create Grade Rate | To create a grade rate, click Create |  | Creation Page Appears
WS-1.08.005 | Create Grade Rate | 1) Click the Legislative Data Group dropdown 2) Click OK |  | Create Grade Rate page appears
WS-1.08.006 | Create Grade Rate | Enter the effective Start Date, Grade Set, Name, Code, Status, Action Reason, Context and attachments |  | Information Entry Successful
WS-1.08.007 | Create Grade Rate Values | 1) To add a grade rate value, click the Add Row 2) To select a grade, click the Grade dropdown 3) Enter the Minimum into the field 4) Enter the Maximum into the field 5) Enter the Midpoint into the field 6) Enter the Value into the field |  | The Grade Rate Value is added successfully
WS-1.08.008 | Create Grade | To access the Review page, click Review |  | Review Page Appears
WS-1.08.009 | Submit Grade | To submit the grade, click Submit. |  | Warning Window Appears
WS-1.08.010 | Submit Grade | To continue with submitting the request, click Yes |  | Submission Successful
WS-1.08.011 | Save Grade | To confirm the request was submitted, click OK |  | Save Successful
WS-1.08.012 | View Grade | To view the new grade, enter the name into the search box. |  | Search successful
WS-1.08.013 | View Grade | To view the grade, click the grade displayed under the Search Results |  | View Results Successful
WS-1.08.014 | Return to the overview page | To return to the Overview page, click Done |  | Return To the Overview Page

## 1.09
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Position
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.09
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Position Through Implementation Projects
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.09.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.09.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | The Manage Implementation Projects page appears
WS-1.09.003 | Navigation | Click on task name - 'Manage Positions' to navigate to task |  | The Implementation Project page appears
WS-1.09.004 | Create Position | To create a Position, click Create |  | Creation Page Appears
WS-1.09.005 | Basic Details | 1) Enter Effective Start Date into the field 2) Select the Business Unit from the dropdown 3) Enter the Name into the field 4) Enter the Code into the field 5) To go to the Position Details page, click Next |  | The Basic Details have been entered
WS-1.09.006 | Position Details | 1) Select the Status from the dropdown 2) Select the Department from the dropdown 3) Select the Job from the dropdown 4) Select the Hiring Status from the dorpdown 5) Enter additional details into the fields 6) To go to the Evaluation Criteria page, click Next |  | The Position Details have been entered
WS-1.09.007 | Evaluation Criteria | 1) Select the Evaluation System dropdown 2) Enter the Evaluation Date 3) Select the Measurement Unit from the dropdown 4) Click Next Note: Perform above steps, if applicable |  | The Evaluation Criteria has been entered
WS-1.09.008 | Profiles | 1) To add a profile to the position select Add Existing Profile or Create Profile 2) Enter the appropriate information into the fields 3) Click Next Note: Perform above steps, if applicable |  | The Profiles have been entered
WS-1.09.009 | Review | 1) To submit the Position, click Submit 2) Click Yes 3) Click OK 4) To go back to the Overview page, click Done |  | The Position has been created

## 1.10
System Test Script - Oracle HCM Cloud - Global HR (Admin)
Manage Organization Trees
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | HCM Cloud Release 13 | Test Script ID # | 1.10
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Manage Organization Trees
| Test Script Instruction |  |  | Validation
Step # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
WS-1.10.001 | Log into Oracle | Login to Oracle Cloud HCM Applications Homepage Click Login Click the Navigator Icon, My Client Groups, Workforce Structures | Enter User Name Enter Password | Login successful
WS-1.10.002 | Navigation | Click on tasklist icon present on the right side of the application window. |  | Search successful
WS-1.10.003 | View Organization Trees Page | Click on task name - 'Manage Organization Trees' to navigate to task |  | Search successful
WS-1.10.004 | Create Organization Tree | Click Create |  | Specify Definition page is displayed
WS-1.10.005 | Enter Specify Definition Information | 1) Enter the Name 2) Enter the Code 3) Click Next |  | Create the Specify Definition Information
WS-1.10.006 | View Specify Labels | View Specify Labels page Click Next |  | View Specify Labels page
WS-1.10.007 | Submit the Organization Tree | 1) Click Submit 2) Click Yes 3) Click OK |  | The new organization tree has been created
WS-1.10.008 | Create Tree Version | 1) Select the organization tree created in earlier step 2) Click Actions 3) Click Create Version |  | Manage Organization Tree: Specify Definition page is displayed
WS-1.10.009 | Enter Specify Definition Information | 1) Enter the Name 2) Enter the Effective Start Date 3) Click Next 4) Click OK |  | Create the Specify Definition Information
WS-1.10.010 | Search for Tree Node Details | 1) Click Search 2) Enter the Name into the field 3) Click Search 4) Select the appropriate tree node 5) Click Add Tree Node |  | Create Tree Node Details
WS-1.10.011 | Click Submit | 1) Click Submit 2) Click Yes 3) Click OK |  | The new specify node has been created.
WS-1.10.012 | Change status to Active | 1) Click Actions 2) Click Flatten 3) Click Row Flattening 4) Click Online Flattening 5) Click OK 6) Click Done 7) Select the organization tree row 8) Click Actions 9) Click Audit 10) Click Online Audit 11) Click OK 12) Click Done 13) Select the organization tree row 14) Click Actions 15) Click Set Status 16) Click Active 17) Click OK |  | The status is changed to Active

## 1.11
System Test Script - Oracle HCM Cloud - Global HR
Generate Organization Hierarchy Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | R13 | Test Script ID # | 1.11
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Generate Organization Hierarchy Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
HR-1.11.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
HR-1.11.02 | Navigate to Navigator | Navigate to the below path Navigator > Tools > Reports and Analytics > Shared Folders > Custom > Human Capital Management > Reports > Human Resoruces > Organization Hierarchy Report |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
HR-1.11.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
HR-1.11.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
HR-1.11.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The Organization report will display all the levels of the department and the number of positions and assigments as per budgets and actuals. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.12
System Test Script - Oracle HCM Cloud - Global HR
Generate Workforce Planning Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | R13 | Test Script ID # | 1.12
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Generate Workforce Planning Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
HR-1.12.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
HR-1.12.02 | Navigate to Navigator | Navigate to the below path Navigator > Tools > Reports and Analytics > Shared Folders > Custom > Human Capital Management > Reports > Human Resoruces > Workforce Planinng Report |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
HR-1.12.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
HR-1.12.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
HR-1.12.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The Workforce Planning report will display all the positions and the incumbents as per the employee and position details currently available in the system. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.13
System Test Script - Oracle HCM Cloud - Global HR
Generate Manpower Budget Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | R13 | Test Script ID # | 1.13
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Generate Manpower Budget Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
HR-1.13.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
HR-1.13.02 | Navigate to Navigator | Navigate to the below path Navigator > Tools > Reports and Analytics > Shared Folders > Custom > Human Capital Management > Reports > Human Resoruces > Manpower Budget Report |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
HR-1.13.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
HR-1.13.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
HR-1.13.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The Manpower budget report will display totals of the positions and the incumbents as per the category (SA, WE, EE etc) for each quarter as we proceed through the year. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.14
System Test Script - Oracle HCM Cloud - Global HR
Generate Salary Beyond the Range Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | R13 | Test Script ID # | 1.14
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Generate Salary Beyond the Range Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
HR-1.14.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
HR-1.14.02 | Navigate to Navigator | Navigate to the below path Navigator > Tools > Reports and Analytics > Shared Folders > Custom > Human Capital Management > Reports > Human Resources > Salary Beyond the Range |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
HR-1.14.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
HR-1.14.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
HR-1.14.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The salary beyond the range report will display all the employees who has a salary basis attached the salary is outside the limits of the salary range for the grade. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.15
System Test Script - Oracle HCM Cloud - Global HR
Generate Missing Department Managers Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | R13 | Test Script ID # | 1.15
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Generate Missing Department Managers Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
HR-1.15.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
HR-1.15.02 | Navigate to Navigator | Navigate to the below path Navigator > Tools > Reports and Analytics > Shared Folders > Custom > Human Capital Management > Reports > Human Resources > Missing department managers report |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
HR-1.15.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
HR-1.15.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
HR-1.15.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report should display all the employees who do not report to the managers of job level 8/9. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,

## 1.16
System Test Script - Oracle HCM Cloud - Global HR
Generate Missing Line Managers Report
Return to Summary
Overview |  |  | Test Script Specification
Software / Release |  | R13 | Test Script ID # | 1.16
Pilot / SIT# / UAT# |  | System Integration Testing (SIT) | Test Script Name | Generate Missing Line Managers Report
| Test Script Instruction |  |  | Test Results
ID # | Action | Navigation Steps | Key Data Elements | Expected Results | Actual Results | Pass/Fail
HR-1.16.01 | Log into Oracle HCM Cloud | Login into Oracle HCM Cloud homepage | User Name | Login successful | Login successful
Password
Click Login
HR-1.16.02 | Navigate to Navigator | Navigate to the below path Navigator > Tools > Reports and Analytics > Shared Folders > Custom > Human Capital Management > Reports > Human Resources > Missing department managers report |  | User should be able to navigate to the report folder | User should be able to navigate to the report folder
HR-1.16.03 | Open the report | Click on the link for the report to see the output. |  | Open the report without any issues | Open the report without any issues
HR-1.16.04 | Employee Slection | The BI Report displays user selectable parameters (if any). |  | Parameters should display correctly pre populated (if any). | Parameters should display correctly pre populated (if any).
HR-1.16.05 | Report Output | The report gets refreshed with the list of all records applicable as per the selected criteria. The report should display all the employees who do not have a line manager available in the system. | Download the report | Report should be generated without any errors or data discrepancie after the parameter is selected. | Report should be generated without any errors or data discrepancie after the parameter is selected.
Download the report by selcting the excel as an option,